## Sheet1
Plan vs Achievement
Date: | 03-Jan-26
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 96940 | 2934984 | 191601 | [6 empty] | 110573 |  |  | 6.28 | 6.75 | 10 | 8.74 | 71% | 69.64% |  |  | 26 | 2
JFL | 44587 | 1496352 | 82525 | [6 empty] | 53388 |  |  | 6.71 | 5.45 | 10 | 8.44 | 73% | 63.13% |  |  | 26 | 2
JKL | 108989 | 2665075 | 217906 | [6 empty] | 142770 |  |  | 7.28 | 6.34 | 10 | 9.34 | 62.15% | 59.19% |  |  | 26 | 2
MFL | 66876 | 2104429 | 132835 | [6 empty] | 85375 |  |  | 8.1 | 6.46 | 10 | 8.05 | 69.25% | 61.65% |  |  | 26 | 2
FFL2 | 94095 | 2701433 | 203095 | [6 empty] | 121709 |  |  | 7.07 | 6.8 | 10 | 10.36 | 68.6% | 57.26% |  |  | 26 | 2
JKL-U2 | 108519 | 3615050 | 208118 | [6 empty] | 123487 |  |  | 7.67 | 8.15 | 10 | 8.07 | 68% | 70.42% |  |  | 26 | 2
LIN | 114910 | 3140225 | 239087 | [6 empty] | 122426 |  |  | 4.15 | 3.58 | 10 | 8.48 | 77% | 69.94% |  |  | 26 | 2
GTAL | 26303 | 0 | 44403 | [6 empty] | 42739 |  |  |  | 5.19 |  | 8.11 |  | 46.93% |  |  | 26 | 2
Grand Total | 661219 |  | 1319570 | [6 empty] | 802467 |  |  | 6.7514 | 6.22 | 10 | 8.77 | 61.12% | 63.48% |  |  | 26 | 2
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-