## Sheet1
Plan vs Achievement
Date: | 06-Jan-26
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 109169 | 3014984 | 503013 | [6 empty] | 125731 |  |  | 6.28 | 6.66 | 10 | 9.39 | 71% | 69.61% |  |  | 26 | 5
JFL | 47258 | 1496352 | 229117 | [6 empty] | 52925 |  |  | 6.71 | 5.48 | 10 | 9.04 | 73% | 65.71% |  |  | 26 | 5
JKL | 97132 | 2665075 | 533035 | [6 empty] | 119097 |  |  | 7.28 | 6.59 | 10 | 10.13 | 62.15% | 62.51% |  |  | 26 | 5
MFL | 62414 | 2104429 | 316049 | [6 empty] | 87542 |  |  | 8.1 | 6.61 | 10 | 8.15 | 69.25% | 58.99% |  |  | 26 | 5
FFL2 | 98045 | 2771433 | 483173 | [6 empty] | 122384 |  |  | 7.07 | 7.09 | 10 | 11.49 | 68.6% | 61.63% |  |  | 26 | 5
JKL-U2 | 111537 | 3693050 | 534282 | [6 empty] | 129793 |  |  | 7.67 | 8.17 | 10 | 8.33 | 68% | 70.18% |  |  | 26 | 5
LIN | 109190 | 3140225 | 565037 | [6 empty] | 122260 |  |  | 4.15 | 3.62 | 10 | 8.46 | 77% | 73.53% |  |  | 26 | 5
GTAL | 19185 | 0 | 101307 | [6 empty] | 44069 |  |  |  | 5.25 |  | 8.04 |  | 41.81% |  |  | 26 | 5
Grand Total | 653930 |  | 3265013 | [6 empty] | 803801 |  |  | 6.7514 | 6.31 | 10 | 9.23 | 61.12% | 64.87% |  |  | 26 | 5
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-