## Sheet1
Plan vs Achievement
Date: | 11-Aug-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 60235 | 1688592 | 543530 | [6 empty] | 61010 |  |  | 8.1 | 8.14 | 9 | 9.64 | 68% | 66.91% |  |  | 25 | 8
JAL3 | 9320 | 206218 | 74090 | [6 empty] | 8328 |  |  | 8.1 | 6.02 | 9 | 8.11 | 68% | 73.51% |  |  | 25 | 8
JFL | 35961 | 1226090 | 315189 | [6 empty] | 35694 |  |  | 7.22 | 6.99 | 10 | 8.69 | 71.8% | 71.7% |  |  | 25 | 8
JKL | 77498 | 1844988 | 584706 | [6 empty] | 86489 |  |  | 8.16 | 7.79 | 8 | 8.6 | 60.3% | 63.85% |  |  | 25 | 8
MFL | 71184 | 2255336 | 582875 | [6 empty] | 81827 |  |  | 7.31 | 6.65 | 10 | 8.93 | 65% | 63% |  |  | 25 | 8
FFL2 | 62125 | 1365460 | 488288 | [6 empty] | 73425 |  |  | 7.52 | 8.01 | 8 | 8.92 | 68% | 63.23% |  |  | 25 | 8
JKL-U2 | 87257 | 2667920 | 697261 | [6 empty] | 98253 |  |  | 9.41 | 8.94 | 8 | 8.32 | 65.3% | 63.17% |  |  | 25 | 8
GMT TOTAL: | 403580 |  | 3285939 | [6 empty] | 445026.16 |  |  | 8.07 | 7.8 | 8.77 | 8.84 | 65.89% | 64.72% |  |  | 25 | 8
LINGERIE | 135140 | 3049596 | 1095482 | [6 empty] | 141490 |  |  | 4.13 | 3.73 | 10 | 11.07 | 73% | 70.08% |  |  | 25 | 8
GTAL | 14900 | 241401 | 164995 | [6 empty] | 23146 |  |  | 6.94 | 7.46 | 8 | 9.35 | 65% | 32.73% |  |  | 25 | 8
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-