## Sheet1
Plan vs Achievement
Date: | 21-Aug-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 61047 | 1688592 | 1109000 | [6 empty] | 68145 |  |  | 8.1 | 8.55 | 9 | 9.59 | 68% | 68.29% |  |  | 25 | 17
JAL3 | 9370 | 206218 | 162370 | [6 empty] | 10408 |  |  | 8.1 | 5.88 | 9 | 8.23 | 68% | 72.66% |  |  | 25 | 17
JFL | 41623 | 1226090 | 653486 | [6 empty] | 39248 |  |  | 7.22 | 7.04 | 10 | 8.53 | 71.8% | 71.91% |  |  | 25 | 17
JKL | 72345 | 1844988 | 1262311 | [6 empty] | 84600 |  |  | 8.16 | 7.62 | 8 | 8.49 | 60.3% | 64.44% |  |  | 25 | 17
MFL | 75605 | 2255336 | 1257534 | [6 empty] | 84954 |  |  | 7.31 | 6.77 | 10 | 8.84 | 65% | 64.61% |  |  | 25 | 17
FFL2 | 53547 | 1365460 | 1051348 | [6 empty] | 68213 |  |  | 7.52 | 7.45 | 8 | 8.42 | 68% | 63.82% |  |  | 25 | 17
JKL-U2 | 90430 | 2667920 | 1504086 | [6 empty] | 103614 |  |  | 9.41 | 9.05 | 8 | 8.48 | 65.3% | 63.98% |  |  | 25 | 17
GMT TOTAL: | 403967 |  | 7000135 | [6 empty] | 459182.29 |  |  | 8.07 | 7.8 | 8.77 | 8.72 | 65.89% | 65.6% |  |  | 25 | 17
LINGERIE | 143260 | 3049596 | 2180713 | [6 empty] | 143516 |  |  | 4.13 | 3.81 | 10 | 10.79 | 73% | 68.92% |  |  | 25 | 17
GTAL | 1906 | 241401 | 186936 | [6 empty] | 4474 |  |  | 6.94 | 7.41 | 8 | 8.64 | 65% | 17.36% |  |  | 25 | 17
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-