## Sheet1
Plan vs Achievement
Date: | 26-Aug-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 53177 | 1688592 | 1336343 | [6 empty] | 56860 |  |  | 8.1 | 8.72 | 9 | 9.42 | 68% | 68.65% |  |  | 25 | 21
JAL3 | 8535 | 206218 | 198605 | [6 empty] | 8512 |  |  | 8.1 | 5.85 | 9 | 8.19 | 68% | 72% |  |  | 25 | 21
JFL | 43369 | 1226090 | 822902 | [6 empty] | 38504 |  |  | 7.22 | 7.02 | 10 | 8.47 | 71.8% | 73.29% |  |  | 25 | 21
JKL | 67082 | 1844988 | 1540834 | [6 empty] | 80847 |  |  | 8.16 | 7.6 | 8 | 8.45 | 60.3% | 63.53% |  |  | 25 | 21
MFL | 75323 | 2255336 | 1554089 | [6 empty] | 84353 |  |  | 7.31 | 6.85 | 10 | 8.85 | 65% | 64.97% |  |  | 25 | 21
FFL2 | 64250 | 1365460 | 1294817 | [6 empty] | 70425 |  |  | 7.52 | 7.42 | 8 | 8.37 | 68% | 63.64% |  |  | 25 | 21
JKL-U2 | 90695 | 2667920 | 1869615 | [6 empty] | 98532 |  |  | 9.41 | 9.16 | 8 | 8.52 | 65.3% | 64.41% |  |  | 25 | 21
GMT TOTAL: | 402431 |  | 8617205 | [6 empty] | 438034.13 |  |  | 8.07 | 7.86 | 8.77 | 8.68 | 65.89% | 65.73% |  |  | 25 | 21
LINGERIE | 119180 | 3049596 | 2708829 | [6 empty] | 115655 |  |  | 4.13 | 3.8 | 10 | 10.82 | 73% | 68.74% |  |  | 25 | 21
GTAL | 5752 | 241401 | 195598 | [6 empty] | 13059 |  |  | 6.94 | 7.35 | 8 | 8.54 | 65% | 14.45% |  |  | 25 | 21
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-