## Sheet1
Plan vs Achievement
Date: | 03-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 67268 | 2061190 | 196458 | [6 empty] | 64243 |  |  | 6.87 | 8.35 | 10 | 9.08 | 68% | 70.49% |  |  | 25 | 3
JAL3 | 9135 | 252869 | 28135 | [6 empty] | 9691 |  |  | 6.44 | 6.84 | 10 | 9.1 | 66% | 72.09% |  |  | 25 | 3
JFL | 41286 | 1022653 | 129518 | [6 empty] | 36851 |  |  | 6.51 | 6.4 | 8 | 8.06 | 71.8% | 77.59% |  |  | 25 | 3
JKL | 69993 | 1740159 | 195192 | [6 empty] | 77006 |  |  | 10.12 | 8.76 | 9 | 8.94 | 58.8% | 61.73% |  |  | 25 | 3
MFL | 73419 | 2149237 | 214221 | [6 empty] | 79860 |  |  | 7.36 | 7.52 | 10 | 9.19 | 64% | 66.54% |  |  | 25 | 3
FFL2 | 73155 | 2425855 | 208725 | [6 empty] | 74274 |  |  | 6.62 | 7.15 | 10 | 8.54 | 68% | 67.55% |  |  | 25 | 3
JKL-U2 | 95035 | 2998611 | 284331 | [6 empty] | 98080 |  |  | 8.92 | 9.1 | 10 | 8.46 | 65% | 67.61% |  |  | 25 | 3
GTAL | 479 | 6632 | 6158 | [6 empty] | 4982 |  |  | 9.11 | 3.03 | 8 | 8.12 | 63% | 3.8% |  |  | 25 | 3
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 114610 | 3797404 | 342932 | [6 empty] | 118067 |  |  | 4.06 | 3.94 | 11 | 9.4 | 78% | 71.73% |  |  | 25 | 3
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-