## Sheet1
Plan vs Achievement
Date: | 11-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 73844 | 2061190 | 605209 | [6 empty] | 73550 |  |  | 6.87 | 8.62 | 10 | 9.73 | 68% | 70.91% |  |  | 25 | 9
JAL3 | 9450 | 252869 | 82750 | [6 empty] | 10494 |  |  | 6.44 | 6.77 | 10 | 9.34 | 66% | 72.18% |  |  | 25 | 9
JFL | 39579 | 1022653 | 368107 | [6 empty] | 37050 |  |  | 6.51 | 6.58 | 8 | 8.21 | 71.8% | 76.68% |  |  | 25 | 9
JKL | 60759 | 1740159 | 572815 | [6 empty] | 65410 |  |  | 10.12 | 9.27 | 9 | 9.38 | 58.8% | 62.64% |  |  | 25 | 9
MFL | 76287 | 2149237 | 667728 | [6 empty] | 80216 |  |  | 7.36 | 7.26 | 10 | 9.08 | 64% | 67.86% |  |  | 25 | 9
FFL2 | 96783 | 2425855 | 715022 | [6 empty] | 100829 |  |  | 6.62 | 7.19 | 10 | 9.8 | 68% | 67.83% |  |  | 25 | 9
JKL-U2 | 93563 | 2998611 | 846919 | [6 empty] | 104958 |  |  | 8.92 | 8.92 | 10 | 8.44 | 65% | 67.52% |  |  | 25 | 9
GTAL | 0 | 6632 | 28396 | [6 empty] | 0 |  |  | 9.11 | 6.95 | 8 | 8.05 | 63% | 4.94% |  |  | 25 | 9
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 137355 | 3797404 | 1117346 | [6 empty] | 140945 |  |  | 4.06 | 4.05 | 11 | 10.32 | 78% | 72.7% |  |  | 25 | 9
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-