## Sheet1
Plan vs Achievement
Date: | 15-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 81582 | 2061190 | 840943 | [6 empty] | 83555 |  |  | 6.87 | 8.39 | 10 | 9.85 | 68% | 70.94% |  |  | 25 | 12
JAL3 | 9405 | 252869 | 110440 | [6 empty] | 10616 |  |  | 6.44 | 6.85 | 10 | 9.52 | 66% | 71.97% |  |  | 25 | 12
JFL | 43944 | 1022653 | 496068 | [6 empty] | 39604 |  |  | 6.51 | 6.42 | 8 | 8.24 | 71.8% | 75.76% |  |  | 25 | 12
JKL | 72461 | 1740159 | 770808 | [6 empty] | 77293 |  |  | 10.12 | 9.47 | 9 | 9.5 | 58.8% | 63.61% |  |  | 25 | 12
MFL | 75693 | 2149237 | 894255 | [6 empty] | 79641 |  |  | 7.36 | 7.24 | 10 | 9.11 | 64% | 68.05% |  |  | 25 | 12
FFL2 | 85935 | 2425855 | 977948 | [6 empty] | 92635 |  |  | 6.62 | 7.2 | 10 | 10.19 | 68% | 67.14% |  |  | 25 | 12
JKL-U2 | 102376 | 2998611 | 1147774 | [6 empty] | 114724 |  |  | 8.92 | 8.73 | 10 | 8.47 | 65% | 67.33% |  |  | 25 | 12
GTAL | 6160 | 6632 | 38336 | [6 empty] | 13426 |  |  | 9.11 | 6.4 | 8 | 8.06 | 63% | 4.33% |  |  | 25 | 12
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 147272 | 3797404 | 1609188 | [6 empty] | 133293 |  |  | 4.06 | 4.09 | 11 | 10.84 | 78% | 72.97% |  |  | 25 | 12
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-