## Sheet1
Plan vs Achievement
Date: | 18-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 89766 | 2061190 | 1097957 | [6 empty] | 91541 |  |  | 6.87 | 8.17 | 10 | 9.95 | 68% | 70.89% |  |  | 25 | 15
JAL3 | 12350 | 252869 | 142085 | [6 empty] | 9977 |  |  | 6.44 | 6.88 | 10 | 9.68 | 66% | 72.28% |  |  | 25 | 15
JFL | 47547 | 1022653 | 641179 | [6 empty] | 41913 |  |  | 6.51 | 6.22 | 8 | 8.31 | 71.8% | 75.55% |  |  | 25 | 15
JKL | 69652 | 1740159 | 988177 | [6 empty] | 72413 |  |  | 10.12 | 9.61 | 9 | 9.73 | 58.8% | 64.59% |  |  | 25 | 15
MFL | 72344 | 2149237 | 1115384 | [6 empty] | 78655 |  |  | 7.36 | 7.26 | 10 | 9.08 | 64% | 68.08% |  |  | 25 | 15
FFL2 | 104730 | 2425855 | 1287763 | [6 empty] | 112956 |  |  | 6.62 | 7.23 | 10 | 10.74 | 68% | 67.33% |  |  | 25 | 15
JKL-U2 | 100330 | 2998611 | 1455430 | [6 empty] | 112343 |  |  | 8.92 | 8.61 | 10 | 8.5 | 65% | 67.09% |  |  | 25 | 15
GTAL | 14853 | 228632 | 72599 | [6 empty] | 32898 |  |  | 9.11 | 5.72 | 8 | 8.15 | 63% | 5.09% |  |  | 25 | 15
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 157990 | 3797404 | 2074208 | [6 empty] | 159942 |  |  | 4.06 | 4.1 | 11 | 11.32 | 78% | 72.95% |  |  | 25 | 15
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-