## Sheet1
Plan vs Achievement
Date: | 21-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 79197 | 2061190 | 1261027 | [6 empty] | 84575 |  |  | 6.87 | 8.05 | 10 | 9.88 | 68% | 70.84% |  |  | 25 | 17
JAL3 | 9895 | 252869 | 162240 | [6 empty] | 9440 |  |  | 6.44 | 6.82 | 10 | 9.6 | 66% | 72.27% |  |  | 25 | 17
JFL | 46504 | 1022653 | 733743 | [6 empty] | 42170 |  |  | 6.51 | 6.18 | 8 | 8.35 | 71.8% | 75.05% |  |  | 25 | 17
JKL | 69016 | 1740159 | 1123431 | [6 empty] | 73856 |  |  | 10.12 | 9.71 | 9 | 9.75 | 58.8% | 65.18% |  |  | 25 | 17
MFL | 78976 | 2149237 | 1271071 | [6 empty] | 84634 |  |  | 7.36 | 7.27 | 10 | 9.12 | 64% | 68.19% |  |  | 25 | 17
FFL2 | 110000 | 2425855 | 1531835 | [6 empty] | 116722 |  |  | 6.62 | 7.21 | 10 | 11.03 | 68% | 67.38% |  |  | 25 | 17
JKL-U2 | 102211 | 2998611 | 1654395 | [6 empty] | 110704 |  |  | 8.92 | 8.57 | 10 | 8.53 | 65% | 66.72% |  |  | 25 | 17
GTAL | 23110 | 228632 | 117539 | [6 empty] | 39864 |  |  | 9.11 | 5.26 | 8 | 8.21 | 63% | 6.53% |  |  | 25 | 17
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 151630 | 3797404 | 2453834 | [6 empty] | 150852 |  |  | 4.06 | 4.08 | 11 | 11.46 | 78% | 73.12% |  |  | 25 | 17
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-