## Sheet1
Plan vs Achievement
Date: | 22-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 78410 | 2061190 | 1339437 | [6 empty] | 82254 |  |  | 6.87 | 7.98 | 10 | 9.83 | 68% | 70.84% |  |  | 25 | 18
JAL3 | 10650 | 252869 | 172890 | [6 empty] | 10273 |  |  | 6.44 | 6.76 | 10 | 9.55 | 66% | 72.34% |  |  | 25 | 18
JFL | 47417 | 1022653 | 781160 | [6 empty] | 40560 |  |  | 6.51 | 6.17 | 8 | 8.37 | 71.8% | 74.84% |  |  | 25 | 18
JKL | 71685 | 1740159 | 1195183 | [6 empty] | 75029 |  |  | 10.12 | 9.67 | 9 | 9.74 | 58.8% | 65.35% |  |  | 25 | 18
MFL | 76639 | 2149237 | 1347710 | [6 empty] | 82059 |  |  | 7.36 | 7.27 | 10 | 9.14 | 64% | 68.12% |  |  | 25 | 18
FFL2 | 95140 | 2425855 | 1626975 | [6 empty] | 97841 |  |  | 6.62 | 7.19 | 10 | 11.04 | 68% | 67.47% |  |  | 25 | 18
JKL-U2 | 106294 | 2998611 | 1760689 | [6 empty] | 114137 |  |  | 8.92 | 8.53 | 10 | 8.55 | 65% | 66.6% |  |  | 25 | 18
GTAL | 21498 | 228632 | 139037 | [6 empty] | 45077 |  |  | 9.11 | 5.18 | 8 | 8.26 | 63% | 7.05% |  |  | 25 | 18
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 153320 | 3797404 | 2607154 | [6 empty] | 153044 |  |  | 4.06 | 4.07 | 11 | 11.53 | 78% | 72.98% |  |  | 25 | 18
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-