## Sheet1
Plan vs Achievement
Date: | 23-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 82176 | 2061190 | 1421613 | [6 empty] | 85813 |  |  | 6.87 | 7.9 | 10 | 9.78 | 68% | 70.82% |  |  | 25 | 19
JAL3 | 10870 | 252869 | 183760 | [6 empty] | 10079 |  |  | 6.44 | 6.7 | 10 | 9.53 | 66% | 72.06% |  |  | 25 | 19
JFL | 47112 | 1022653 | 828272 | [6 empty] | 41017 |  |  | 6.51 | 6.15 | 8 | 8.37 | 71.8% | 74.76% |  |  | 25 | 19
JKL | 71762 | 1740159 | 1267152 | [6 empty] | 79332 |  |  | 10.12 | 9.65 | 9 | 9.74 | 58.8% | 65.42% |  |  | 25 | 19
MFL | 76487 | 2149237 | 1424197 | [6 empty] | 81947 |  |  | 7.36 | 7.28 | 10 | 9.16 | 64% | 68.07% |  |  | 25 | 19
FFL2 | 96675 | 2425855 | 1723650 | [6 empty] | 106398 |  |  | 6.62 | 7.18 | 10 | 11.09 | 68% | 67.41% |  |  | 25 | 19
JKL-U2 | 109871 | 2998611 | 1870560 | [6 empty] | 120429 |  |  | 8.92 | 8.5 | 10 | 8.58 | 65% | 66.57% |  |  | 25 | 19
GTAL | 22968 | 228632 | 162005 | [6 empty] | 44675 |  |  | 9.11 | 5.11 | 8 | 8.31 | 63% | 7.6% |  |  | 25 | 19
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 138564 | 3797404 | 2745718 | [6 empty] | 139203 |  |  | 4.06 | 4.07 | 11 | 11.51 | 78% | 73.12% |  |  | 25 | 19
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-