## Sheet1
Plan vs Achievement
Date: | 25-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 84660 | 2061190 | 1588303 | [6 empty] | 84905 |  |  | 6.87 | 7.79 | 10 | 9.74 | 68% | 70.8% |  |  | 25 | 21
JAL3 | 11170 | 252869 | 207235 | [6 empty] | 10870 |  |  | 6.44 | 6.57 | 10 | 9.44 | 66% | 72.37% |  |  | 25 | 21
JFL | 46360 | 1022653 | 920803 | [6 empty] | 42980 |  |  | 6.51 | 6.09 | 8 | 8.34 | 71.8% | 74.72% |  |  | 25 | 21
JKL | 65697 | 1740159 | 1403282 | [6 empty] | 76140 |  |  | 10.12 | 9.6 | 9 | 9.69 | 58.8% | 65.39% |  |  | 25 | 21
MFL | 76400 | 2149237 | 1574664 | [6 empty] | 81760 |  |  | 7.36 | 7.29 | 10 | 9.13 | 64% | 68.1% |  |  | 25 | 21
FFL2 | 92970 | 2425855 | 1911980 | [6 empty] | 103996 |  |  | 6.62 | 7.18 | 10 | 11.17 | 68% | 67.3% |  |  | 25 | 21
JKL-U2 | 107017 | 2998611 | 2084339 | [6 empty] | 120534 |  |  | 8.92 | 8.45 | 10 | 8.6 | 65% | 66.48% |  |  | 25 | 21
GTAL | 34441 | 228632 | 228000 | [6 empty] | 48446 |  |  | 9.11 | 5 | 8 | 8.4 | 63% | 9.22% |  |  | 25 | 21
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 158480 | 3797404 | 3064548 | [6 empty] | 154052 |  |  | 4.06 | 4.06 | 11 | 11.63 | 78% | 73.09% |  |  | 25 | 21
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-