## Sheet1
Plan vs Achievement
Date: | 02-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 99091 | 2343382 | 189847 | 2153535 | 180260.1538 | -9586.8462 | 90105.04 | 640646.8344 | 662918.79 | 93080 | 99.1% | 9010.504 | 7.11 | 6.69 | 10 | 10.29 | 68% | 72.86% | 1270076.43 | 1281649.6938 | 26 | 2 | 24
JAL3 | 11780 | 285887 | 22170 | 263717 | 21991.3077 | -178.6923 | 11019.88 | 65678.4848 | 67146 | 9334 | 96.41% | 1101.988 | 5.96 | 5.7 | 10 | 8.39 | 68% | 78.86% | 126369 | 131068.1938 | 26 | 2 | 24
JFL | 45696 | 1652169 | 91201 | 1560968 | 127089.9231 | 35888.9231 | 64266.56 | 390098.0192 | 263665.92 | 39870 | 68.21% | 6120.6248 | 6.07 | 5.77 | 10.5 | 8.1 | 72% | 75.93% | 526229.77 | 771435.8331 | 26 | 2 | 24
JKL | 62711 | 1755763 | 128111 | 1627652 | 135058.6923 | 6947.6923 | 67614.52 | 697781.8464 | 552483.91 | 72171 | 80.98% | 7512.7244 | 10.32 | 8.81 | 9 | 8.85 | 60% | 61.96% | 1128657.91 | 1393805.7046 | 26 | 2 | 24
MFL | 82124 | 2319422 | 169737 | 2149685 | 178417.0769 | 8680.0769 | 89272.36 | 669542.7 | 581437.92 | 90642 | 89.81% | 8927.236 | 7.5 | 7.08 | 10 | 9.89 | 64% | 68.77% | 1201737.96 | 1338128.0769 | 26 | 2 | 24
FFL2 | 89581 | 2196792 | 182761 | 2014031 | 168984 | -13777 | 84144.48 | 663058.5024 | 662899.4 | 91383 | 101.6% | 8414.448 | 7.88 | 7.4 | 10 | 12.08 | 68% | 67.57% | 1352431.4 | 1331593.92 | 26 | 2 | 24
JKL-U2 | 116620 | 3634362 | 232097 | 3402265 | 279566.3077 | 47469.3077 | 140755.4 | 1220349.318 | 872317.6 | 123376 | 71.63% | 14075.54 | 8.67 | 7.48 | 10 | 8.54 | 65% | 69.53% | 1736085.56 | 2423839.8877 | 26 | 2 | 24
GTAL | 18162 | 335974 | 38291 | 297683 | 25844.1538 | -12446.8462 | 12633.8 | 83509.418 | 19796.58 | 28865 | 24.43% | 1579.225 | 6.61 | 1.09 | 8 | 8 | 63% | 14.63% | 41737.19 | 170829.8569 | 26 | 2 | 24
GMT TOTAL: | 525765 | 14523751 | 1054215 | 13469536 | 1117211.6154 | 62996.6154 | 559812.04 | 4416916.9956 | 3287345.6625 | 548721 | 74.78% | 56603.8463 | 7.89 | 6.2525 | 9.89 | 9.2675 | 65.66% | 63.76% | 6591479.2875 | 8814799.6454 | 26 | 2 | 24
LINGERIE | 119173 | 3013766 | 248133 | 2765633 | 231828.1538 | -16304.8462 | 115392.24 | 448875.8136 | 495759.68 | 111350 | 114.5% | 13083.0204 | 3.89 | 4.16 | 8.82 | 10.23 | 74% | 76.44% | 1032233.28 | 901811.5185 | 26 | 2 | 24
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
14523751 | 1054215 | 520000 | 12480000 | 13534215 | 989536
- |  | 555000 | 13320000 | 14374215 | 149536
- |  | 590000 | 14160000 | 15214215 | -690464
- |  | 625000 | 15000000 | 16054215 | -1530464
- |  | 660000 | 15840000 | 16894215 | -2370464
- |  | 695000 | 16680000 | 17734215 | -3210464