## Sheet1
Plan vs Achievement
Date: | 05-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 102444 | 2343382 | 386176 | 1957206 | 360520.3077 | -25655.6923 | 89550 | 636700.5 | 681252.6 | 100065 | 100.2% | 8955 | 7.11 | 6.65 | 10 | 10.43 | 68% | 73.01% | 2568070.4 | 2563299.3877 | 26 | 4 | 22
JAL3 | 13490 | 285887 | 47810 | 238077 | 43982.6154 | -3827.3846 | 10937.6957 | 65188.6661 | 77837.3 | 9144 | 105.2% | 1093.7696 | 5.96 | 5.77 | 10 | 8.87 | 68% | 79.77% | 275863.7 | 262136.3877 | 26 | 4 | 22
JFL | 46818 | 1652169 | 189244 | 1462925 | 254179.8462 | 64935.8462 | 65641 | 398440.87 | 259371.72 | 41296 | 67.95% | 6251.5238 | 6.07 | 5.54 | 10.5 | 8.22 | 72% | 75.05% | 1048411.76 | 1542871.6662 | 26 | 4 | 22
JKL | 66807 | 1755763 | 263463 | 1492300 | 270117.3846 | 6654.3846 | 67787.2609 | 699564.5322 | 594582.3 | 74515 | 84.12% | 7531.9179 | 10.32 | 8.9 | 9 | 8.98 | 60% | 62.92% | 2344820.7 | 2787611.4092 | 26 | 4 | 22
MFL | 93947 | 2319422 | 372028 | 1947394 | 356834.1538 | -15193.8462 | 88753.9565 | 665654.6739 | 645415.89 | 100692 | 95.5% | 8875.3957 | 7.5 | 6.87 | 10 | 10.21 | 64% | 68.01% | 2555832.36 | 2676256.1538 | 26 | 4 | 22
FFL2 | 86555 | 2196792 | 360497 | 1836295 | 337968 | -22529 | 83602.1739 | 658785.1304 | 634448.15 | 92261 | 99.22% | 8360.2174 | 7.88 | 7.33 | 10 | 12.1 | 68% | 65.72% | 2642443.01 | 2663187.84 | 26 | 4 | 22
JKL-U2 | 104555 | 3634362 | 445865 | 3188497 | 559132.6154 | 113267.6154 | 143176.1739 | 1241337.4278 | 793572.45 | 112865 | 69.81% | 14317.6174 | 8.67 | 7.59 | 10 | 8.46 | 65% | 69.23% | 3384115.35 | 4847679.7754 | 26 | 4 | 22
GTAL | 921 | 335974 | 55287 | 280687 | 51688.3077 | -3598.6923 | 12243.8261 | 80931.6904 | 994.68 | 23664 | 17.48% | 1530.4783 | 6.61 | 1.08 | 8 | 8.06 | 63% | 10.23% | 59709.96 | 341659.7138 | 26 | 4 | 22
GMT TOTAL: | 515537 | 14523751 | 2120370 | 12403381 | 2234423.2308 | 114053.2308 | 561692.087 | 4431750.5661 | 3204706.8762 | 554502 | 74.76% | 56793.9421 | 7.89 | 6.2162 | 9.89 | 9.4163 | 65.66% | 62.99% | 13180750.0125 | 17629599.2908 | 26 | 4 | 22
LINGERIE | 128250 | 3013766 | 497683 | 2516083 | 463656.3077 | -34026.6923 | 114971 | 447237.19 | 532237.5 | 123113 | 114.5% | 13035.2608 | 3.89 | 4.15 | 8.82 | 10.12 | 74% | 75.57% | 2065384.45 | 1803623.0369 | 26 | 4 | 22
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
14523751 | 2120370 | 510000 | 11220000 | 13340370 | 1183381
- |  | 545000 | 11990000 | 14110370 | 413381
- |  | 580000 | 12760000 | 14880370 | -356619
- |  | 615000 | 13530000 | 15650370 | -1126619
- |  | 650000 | 14300000 | 16420370 | -1896619
- |  | 685000 | 15070000 | 17190370 | -2666619