## Sheet1
Plan vs Achievement
Date: | 08-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 89621 | 2343382 | 661238 | [6 empty] | 86452 |  |  | 7.11 | 6.83 | 10 | 10.56 | 68% | 72.68% |  |  | 26 | 7
JAL3 | 11535 | 285887 | 82830 | [6 empty] | 10449 |  |  | 5.96 | 5.99 | 10 | 9.29 | 68% | 77.2% |  |  | 26 | 7
JFL | 57281 | 1652169 | 348274 | [6 empty] | 48309 |  |  | 6.07 | 5.5 | 10.5 | 8.54 | 72% | 76.65% |  |  | 26 | 7
JKL | 59106 | 1755763 | 460935 | [6 empty] | 68630 |  |  | 10.32 | 9.18 | 9 | 9.3 | 60% | 61.91% |  |  | 26 | 7
MFL | 72593 | 2319422 | 611966 | [6 empty] | 77789 |  |  | 7.5 | 6.88 | 10 | 9.85 | 64% | 67.46% |  |  | 26 | 7
FFL2 | 95939 | 2196792 | 650149 | [6 empty] | 107998 |  |  | 7.88 | 7.23 | 10 | 12.35 | 68% | 64.92% |  |  | 26 | 7
JKL-U2 | 102371 | 3634362 | 760970 | [6 empty] | 106555 |  |  | 8.67 | 7.75 | 10 | 8.49 | 65% | 69.05% |  |  | 26 | 7
GTAL | 0 | 335974 | 55397 | [6 empty] | 0 |  |  | 6.61 | 1.08 | 8 | 8.03 | 63% | 5.87% |  |  | 26 | 7
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 141550 | 3013766 | 914595 | [6 empty] | 134858 |  |  | 3.89 | 4.11 | 8.82 | 10.35 | 74% | 76.07% |  |  | 26 | 7
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-