## Sheet1
Plan vs Achievement
Date: | 11-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 84088 | 2343382 | 850590 | 1492792 | 811170.6923 | -39419.3077 | 87604.4444 | 622867.6 | 577684.56 | 83135 | 101.3% | 8760.4444 | 7.11 | 6.87 | 10 | 10.53 | 68% | 72.55% | 5843553.3 | 5767423.6223 | 26 | 9 | 17
JAL3 | 10765 | 285887 | 105075 | 180812 | 98960.8846 | -6114.1154 | 10643.1667 | 63433.2733 | 64590 | 10087 | 106.9% | 1064.3167 | 5.96 | 6 | 10 | 9.35 | 68% | 76.58% | 630450 | 589806.8723 | 26 | 9 | 17
JFL | 52868 | 1652169 | 456850 | 1195319 | 571904.6538 | 115054.6538 | 69343.7222 | 420916.3939 | 289716.64 | 45841 | 72.12% | 6604.164 | 6.07 | 5.48 | 10.5 | 8.61 | 72% | 77.39% | 2503538 | 3471461.2488 | 26 | 9 | 17
JKL | 62007 | 1755763 | 578510 | 1177253 | 607764.1154 | 29254.1154 | 68847.7778 | 710509.0667 | 585346.08 | 70171 | 87.07% | 7649.7531 | 10.32 | 9.44 | 9 | 9.82 | 60% | 61.57% | 5461134.4 | 6272125.6708 | 26 | 9 | 17
MFL | 64215 | 2319422 | 748006 | 1571416 | 802876.8462 | 54870.8462 | 90868.3889 | 681512.9167 | 446936.4 | 68948 | 86.46% | 9086.8389 | 7.5 | 6.96 | 10 | 9.63 | 64% | 67.72% | 5206121.76 | 6021576.3462 | 26 | 9 | 17
FFL2 | 90575 | 2196792 | 848619 | 1348173 | 760428 | -88191 | 79930.4444 | 629851.9022 | 660291.75 | 96029 | 103.2% | 7993.0444 | 7.88 | 7.29 | 10 | 12.51 | 68% | 63.99% | 6186432.51 | 5992172.64 | 26 | 9 | 17
JKL-U2 | 95281 | 3634362 | 958305 | 2676057 | 1258048.3846 | 299743.3846 | 153963.2222 | 1334861.1367 | 745097.42 | 105241 | 68.71% | 15396.3222 | 8.67 | 7.82 | 10 | 8.57 | 65% | 68.78% | 7493945.1 | 10907279.4946 | 26 | 9 | 17
GTAL | 0 | 335974 | 55397 | 280577 | 116298.6923 | 60901.6923 | 15587.6111 | 103034.1094 | 0 | 0 | 7.783% | 1948.4514 | 6.61 | 1.08 | 8 | 8.03 | 63% | 4.6% | 59828.76 | 768734.3562 | 26 | 9 | 17
GMT TOTAL: | 459799 | 14523751 | 4601352 | 9922399 | 5027452.2692 | 426100.2692 | 576788.7778 | 4550863.4567 | 2927770.1325 | 479452 | 73.86% | 58320.4022 | 7.89 | 6.3675 | 9.89 | 9.6313 | 65.66% | 61.65% | 29299108.86 | 39666598.4042 | 26 | 9 | 17
LINGERIE | 129300 | 3013766 | 1179930 | 1833836 | 1043226.6923 | -136703.3077 | 109063.1111 | 424255.5022 | 531423 | 115859 | 119.5% | 12365.4321 | 3.89 | 4.11 | 8.82 | 10.47 | 74% | 75.64% | 4849512.3 | 4058151.8331 | 26 | 9 | 17
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
14523751 | 4601352 | 450000 | 7650000 | 12251352 | 2272399
- |  | 485000 | 8245000 | 12846352 | 1677399
- |  | 520000 | 8840000 | 13441352 | 1082399
- |  | 555000 | 9435000 | 14036352 | 487399
- |  | 590000 | 10030000 | 14631352 | -107601
- |  | 625000 | 10625000 | 15226352 | -702601