## Sheet1
Plan vs Achievement
Date: | 15-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 87966 | 2343382 | 1193275 | [6 empty] | 88751 |  |  | 7.11 | 6.96 | 10 | 10.42 | 68% | 72.43% |  |  | 26 | 13
JAL3 | 10810 | 285887 | 149895 | [6 empty] | 9302 |  |  | 5.96 | 5.94 | 10 | 9.23 | 68% | 76.33% |  |  | 26 | 13
JFL | 55519 | 1652169 | 687622 | [6 empty] | 52660 |  |  | 6.07 | 5.39 | 10.5 | 8.84 | 72% | 77.44% |  |  | 26 | 13
JKL | 59171 | 1755763 | 834739 | [6 empty] | 68757 |  |  | 10.32 | 9.69 | 9 | 10.16 | 60% | 60.29% |  |  | 26 | 13
MFL | 80065 | 2319422 | 1056065 | [6 empty] | 83235 |  |  | 7.5 | 7.06 | 10 | 9.45 | 64% | 68.2% |  |  | 26 | 13
FFL2 | 81300 | 2196792 | 1167482 | [6 empty] | 90944 |  |  | 7.88 | 7.51 | 10 | 12.62 | 68% | 62.72% |  |  | 26 | 13
JKL-U2 | 109990 | 3634362 | 1374850 | [6 empty] | 122872 |  |  | 8.67 | 7.84 | 10 | 8.68 | 65% | 67.36% |  |  | 26 | 13
GTAL | 1878 | 335974 | 58227 | [6 empty] | 4363 |  |  | 6.61 | 3.27 | 8 | 8.04 | 63% | 3.53% |  |  | 26 | 13
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 120646 | 3013766 | 1669545 | [6 empty] | 119429 |  |  | 3.89 | 4.12 | 8.82 | 10.3 | 74% | 75.41% |  |  | 26 | 13
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-