## Sheet1
Plan vs Achievement
Date: | 16-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 89020 | 2343382 | 1282295 | [6 empty] | 91311 |  |  | 7.11 | 6.98 | 10 | 10.42 | 68% | 72.3% |  |  | 26 | 14
JAL3 | 11255 | 285887 | 161150 | [6 empty] | 9793 |  |  | 5.96 | 5.94 | 10 | 9.24 | 68% | 76.25% |  |  | 26 | 14
JFL | 53872 | 1652169 | 741494 | [6 empty] | 47693 |  |  | 6.07 | 5.38 | 10.5 | 8.86 | 72% | 77.25% |  |  | 26 | 14
JKL | 57654 | 1755763 | 892628 | [6 empty] | 69400 |  |  | 10.32 | 9.72 | 9 | 10.18 | 60% | 59.91% |  |  | 26 | 14
MFL | 78288 | 2319422 | 1134353 | [6 empty] | 81407 |  |  | 7.5 | 7.08 | 10 | 9.42 | 64% | 68.39% |  |  | 26 | 14
FFL2 | 76680 | 2196792 | 1244162 | [6 empty] | 88584 |  |  | 7.88 | 7.58 | 10 | 12.63 | 68% | 62.65% |  |  | 26 | 14
JKL-U2 | 107325 | 3634362 | 1482455 | [6 empty] | 114609 |  |  | 8.67 | 7.85 | 10 | 8.73 | 65% | 67.17% |  |  | 26 | 14
GTAL | 2870 | 335974 | 61097 | [6 empty] | 5867 |  |  | 6.61 | 3.27 | 8 | 8.07 | 63% | 3.57% |  |  | 26 | 14
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 117405 | 3013766 | 1786950 | [6 empty] | 118670 |  |  | 3.89 | 4.12 | 8.82 | 10.25 | 74% | 75.38% |  |  | 26 | 14
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-