## Sheet1
Plan vs Achievement
Date: | 28-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 84003 | 2343382 | 2172096 | 171286 | 2163121.8462 | -8974.1538 | 85096.3333 | 605034.93 | 598101.36 | 83364 | 100.6% | 8509.6333 | 7.11 | 7.12 | 10 | 10.4 | 68% | 71.95% | 15465323.52 | 15379796.3262 | 26 | 24 | 2
JAL3 | 10190 | 285887 | 263430 | 22457 | 263895.6923 | 465.6923 | 10882.3333 | 64858.7067 | 61751.4 | 9699 | 101.5% | 1088.2333 | 5.96 | 6.06 | 10 | 8.9 | 68% | 75.71% | 1596385.8 | 1572818.3262 | 26 | 24 | 2
JFL | 53655 | 1652169 | 1345704 | 306465 | 1525079.0769 | 179375.0769 | 120040 | 728642.8 | 285981.15 | 49549 | 77.48% | 11432.381 | 6.07 | 5.33 | 10.5 | 9.24 | 72% | 77.6% | 7172602.32 | 9257229.9969 | 26 | 24 | 2
JKL | 52694 | 1755763 | 1474540 | 281223 | 1620704.3077 | 146164.3077 | 111305.6667 | 1148674.48 | 513766.5 | 62314 | 85.96% | 12367.2963 | 10.32 | 9.75 | 9 | 8.66 | 60% | 57.34% | 14376765 | 16725668.4554 | 26 | 24 | 2
MFL | 74756 | 2319422 | 1934349 | 385073 | 2141004.9231 | 206655.9231 | 153276.3333 | 1149572.5 | 538243.2 | 85036 | 86.73% | 15327.6333 | 7.5 | 7.2 | 10 | 9.5 | 64% | 67.71% | 13927312.8 | 16057536.9231 | 26 | 24 | 2
FFL2 | 71564 | 2196792 | 2042889 | 153903 | 2027808 | -15081 | 75155.6667 | 592226.6533 | 567502.52 | 84017 | 101.4% | 7515.5667 | 7.88 | 7.93 | 10 | 12.38 | 68% | 62.56% | 16200109.77 | 15979127.04 | 26 | 24 | 2
JKL-U2 | 101604 | 3634362 | 2508647 | 1125715 | 3354795.6923 | 846148.6923 | 409106.3333 | 3546951.91 | 817912.2 | 111910 | 69.43% | 40910.6333 | 8.67 | 8.05 | 10 | 8.79 | 65% | 66.53% | 20194608.35 | 29086078.6523 | 26 | 24 | 2
GTAL | 14473 | 335974 | 152936 | 183038 | 310129.8462 | 157193.8462 | 65837 | 435182.57 | 83075.02 | 21499 | 42.82% | 8229.625 | 6.61 | 5.74 | 8 | 8.06 | 63% | 8.09% | 877852.64 | 2049958.2831 | 26 | 24 | 2
GMT TOTAL: | 462939 | 14523751 | 11894591 | 2629160 | 13406539.3846 | 1511948.3846 | 1030699.6667 | 8132220.37 | 3308856.5025 | 507388 | 80.37% | 104216.3465 | 7.89 | 7.1475 | 9.89 | 9.4913 | 65.66% | 60.94% | 85016589.1725 | 105777595.7446 | 26 | 24 | 2
LINGERIE | 113611 | 3013766 | 2950635 | 63131 | 2781937.8462 | -168697.1538 | 58914 | 229175.46 | 466941.21 | 109440 | 112.1% | 6679.5918 | 3.89 | 4.11 | 8.82 | 9.72 | 74% | 76.1% | 12127109.85 | 10821738.2215 | 26 | 24 | 2
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
14523751 | 11894591 | 460000 | 920000 | 12814591 | 1709160
- |  | 495000 | 990000 | 12884591 | 1639160
- |  | 530000 | 1060000 | 12954591 | 1569160
- |  | 565000 | 1130000 | 13024591 | 1499160
- |  | 600000 | 1200000 | 13094591 | 1429160
- |  | 635000 | 1270000 | 13164591 | 1359160