## Sheet1
Plan vs Achievement
Date: | 30-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 77191 | 2347879 | 2334562 | [6 empty] | 78821 |  |  | 7.11 | 7.19 | 10 | 10.43 | 68% | 71.82% |  |  | 26 | 26
JAL3 | 10975 | 286786 | 285785 | [6 empty] | 5826 |  |  | 5.96 | 6.06 | 10 | 8.91 | 68% | 75.72% |  |  | 26 | 26
JFL | 54926 | 1652169 | 1455860 | [6 empty] | 46720 |  |  | 6.07 | 5.33 | 10.5 | 9.17 | 72% | 78.08% |  |  | 26 | 26
JKL | 54874 | 1581368 | 1583773 | [6 empty] | 64695 |  |  | 10.32 | 9.73 | 9 | 9.86 | 60% | 57.17% |  |  | 26 | 26
MFL | 67956 | 2087877 | 2069640 | [6 empty] | 76477 |  |  | 7.5 | 7.23 | 10 | 9.42 | 64% | 67.58% |  |  | 26 | 26
FFL2 | 68219 | 2190430 | 2182317 | [6 empty] | 76277 |  |  | 7.88 | 7.99 | 10 | 12.31 | 68% | 62.48% |  |  | 26 | 26
JKL-U2 | 103147 | 2774015 | 2711800 | [6 empty] | 112213 |  |  | 8.67 | 8.09 | 10 | 8.8 | 65% | 66.49% |  |  | 26 | 26
GTAL | 18031 | 204776 | 184074 | [6 empty] | 30120 |  |  | 6.61 | 5.94 | 8 | 8.1 | 63% | 9.39% |  |  | 26 | 26
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 118000 | 3191765 | 3186629 | [6 empty] | 116993 |  |  | 3.89 | 4.1 | 8.82 | 9.67 | 74% | 76.1% |  |  | 26 | 26
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-