## Sheet1
Plan vs Achievement
Date: | 03-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 66703 | 2203539 | 214569 | [6 empty] | 68014 |  |  | 7.6 | 8.57 | 10 | 10.1 | 72% | 71.4% |  |  | 26 | 3
JAL3 | 13630 | 313636 | 39910 | [6 empty] | 11285 |  |  | 6.47 | 6.14 | 10 | 11 | 72% | 76.18% |  |  | 26 | 3
JFL | 43487 | 1498277 | 132655 | [6 empty] | 45718 |  |  | 6.49 | 5.68 | 10 | 8.86 | 73% | 67.71% |  |  | 26 | 3
JKL | 56990 | 2014480 | 166596 | [6 empty] | 65753 |  |  | 9.27 | 8.91 | 10 | 8.47 | 65% | 54.81% |  |  | 26 | 3
MFL | 66163 | 2332178 | 212923 | [6 empty] | 74086 |  |  | 7.82 | 7.54 | 10 | 9.11 | 72% | 65.35% |  |  | 26 | 3
FFL2 | 74555 | 2597126 | 224451 | [6 empty] | 79311 |  |  | 7.34 | 8.62 | 10 | 11.8 | 73% | 65.25% |  |  | 26 | 3
JKL-U2 | 98350 | 3793698 | 300827 | [6 empty] | 108306 |  |  | 8.14 | 8.93 | 10 | 9.15 | 72% | 66.98% |  |  | 26 | 3
GTAL | 7235 | 36509 | 27964 | [6 empty] | 21296 |  |  | 7.67 | 7.27 | 10 | 8.08 | 63% | 15.05% |  |  | 26 | 3
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 141450 | 3461205 | 399495 | [6 empty] | 127076 |  |  | 4.22 | 3.89 | 10 | 10 | 80% | 77% |  |  | 26 | 3
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-