## Sheet1
Plan vs Achievement
Date: | 05-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 70615 | 2203539 | 351885 | [6 empty] | 72106 |  |  | 7.6 | 8.63 | 10 | 10.05 | 72% | 71.13% |  |  | 26 | 5
JAL3 | 14730 | 313636 | 69185 | [6 empty] | 12162 |  |  | 6.47 | 6.15 | 10 | 11.51 | 72% | 75.78% |  |  | 26 | 5
JFL | 42808 | 1498277 | 219215 | [6 empty] | 41651 |  |  | 6.49 | 5.8 | 10 | 8.93 | 73% | 69.21% |  |  | 26 | 5
JKL | 57827 | 2014480 | 282916 | [6 empty] | 68324 |  |  | 9.27 | 8.9 | 10 | 8.44 | 65% | 55.71% |  |  | 26 | 5
MFL | 60827 | 2332178 | 344918 | [6 empty] | 71436 |  |  | 7.82 | 7.72 | 10 | 9.24 | 72% | 65.39% |  |  | 26 | 5
FFL2 | 86685 | 2597126 | 392725 | [6 empty] | 90193 |  |  | 7.34 | 8.54 | 10 | 12.04 | 73% | 66.48% |  |  | 26 | 5
JKL-U2 | 97662 | 3823698 | 495313 | [6 empty] | 108754 |  |  | 8.14 | 9.04 | 10 | 9.24 | 72% | 66.56% |  |  | 26 | 5
GTAL | 5181 | 36509 | 39856 | [6 empty] | 15241 |  |  | 7.67 | 6.89 | 10 | 8.05 | 63% | 12.98% |  |  | 26 | 5
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 128550 | 3461205 | 668730 | [6 empty] | 115190 |  |  | 4.22 | 3.89 | 10 | 10.03 | 80% | 77.47% |  |  | 26 | 5
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-