## Sheet1
Plan vs Achievement
Date: | 13-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 80215 | 2203539 | 881029 | [6 empty] | 83144 |  |  | 7.6 | 8.25 | 10 | 10.2 | 72% | 70.66% |  |  | 26 | 12
JAL3 | 8990 | 313636 | 145970 | [6 empty] | 7477 |  |  | 6.47 | 6.16 | 10 | 10.29 | 72% | 73.54% |  |  | 26 | 12
JFL | 35729 | 1498277 | 486284 | [6 empty] | 34843 |  |  | 6.49 | 5.89 | 10 | 8.67 | 73% | 69.38% |  |  | 26 | 12
JKL | 47008 | 2014480 | 637807 | [6 empty] | 57530 |  |  | 9.27 | 9.38 | 10 | 8.44 | 65% | 56.46% |  |  | 26 | 12
MFL | 73877 | 2332178 | 826491 | [6 empty] | 78770 |  |  | 7.82 | 7.73 | 10 | 9.18 | 72% | 66.53% |  |  | 26 | 12
FFL2 | 99420 | 2597126 | 1059809 | [6 empty] | 106212 |  |  | 7.34 | 7.73 | 10 | 12.27 | 73% | 67.46% |  |  | 26 | 12
JKL-U2 | 101260 | 3823698 | 1189756 | [6 empty] | 110315 |  |  | 8.14 | 8.99 | 10 | 9.37 | 72% | 66.65% |  |  | 26 | 12
GTAL | 0 | 48509 | 49072 | [6 empty] | 0 |  |  | 7.67 | 7.12 | 10 | 8.02 | 63% | 7.03% |  |  | 26 | 12
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 120612 | 3461205 | 1615779 | [6 empty] | 112145 |  |  | 4.22 | 3.82 | 10 | 10.15 | 80% | 76.55% |  |  | 26 | 12
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-