## Sheet1
Plan vs Achievement
Date: | 17-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 77687 | 2203539 | 1104113 | [6 empty] | 81261 |  |  | 7.6 | 8.23 | 10 | 10.28 | 72% | 70.36% |  |  | 26 | 15
JAL3 | 11688 | 313636 | 174753 | [6 empty] | 9530 |  |  | 6.47 | 6.24 | 10 | 10.1 | 72% | 73.05% |  |  | 26 | 15
JFL | 40605 | 1498277 | 602399 | [6 empty] | 39995 |  |  | 6.49 | 6.04 | 10 | 8.79 | 73% | 69.02% |  |  | 26 | 15
JKL | 46779 | 2014480 | 778640 | [6 empty] | 52955 |  |  | 9.27 | 9.59 | 10 | 8.43 | 65% | 56.8% |  |  | 26 | 15
MFL | 73866 | 2332178 | 1049549 | [6 empty] | 76528 |  |  | 7.82 | 7.67 | 10 | 9.16 | 72% | 67.2% |  |  | 26 | 15
FFL2 | 90092 | 2597126 | 1352677 | [6 empty] | 96672 |  |  | 7.34 | 7.58 | 10 | 12.16 | 73% | 67.44% |  |  | 26 | 15
JKL-U2 | 105166 | 3823698 | 1503324 | [6 empty] | 112067 |  |  | 8.14 | 8.96 | 10 | 9.4 | 72% | 66.48% |  |  | 26 | 15
GTAL | 4924 | 48509 | 69511 | [6 empty] | 23546 |  |  | 7.67 | 5.92 | 10 | 7.96 | 63% | 7.05% |  |  | 26 | 15
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 131110 | 3461205 | 2018699 | [6 empty] | 130215 |  |  | 4.22 | 3.8 | 10 | 10.2 | 80% | 75.93% |  |  | 26 | 15
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-