## Sheet1
Plan vs Achievement
Date: | 24-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 96073 | 2203539 | 1615051 | [6 empty] | 98820 |  |  | 7.6 | 8.06 | 10 | 10.47 | 72% | 70.42% |  |  | 26 | 21
JAL3 | 12290 | 313636 | 246691 | [6 empty] | 10029 |  |  | 6.47 | 6.53 | 10 | 10.69 | 72% | 72.64% |  |  | 26 | 21
JFL | 40368 | 1498277 | 848765 | [6 empty] | 39131 |  |  | 6.49 | 6.26 | 10 | 9.11 | 73% | 67.56% |  |  | 26 | 21
JKL | 69951 | 2014480 | 1135196 | [6 empty] | 78661 |  |  | 9.27 | 9.62 | 10 | 8.8 | 65% | 57.41% |  |  | 26 | 21
MFL | 77844 | 2332178 | 1511726 | [6 empty] | 84459 |  |  | 7.82 | 7.55 | 10 | 9.23 | 72% | 67.76% |  |  | 26 | 21
FFL2 | 109210 | 2597126 | 1946211 | [6 empty] | 109912 |  |  | 7.34 | 7.34 | 10 | 12.02 | 73% | 68.05% |  |  | 26 | 21
JKL-U2 | 124018 | 3823698 | 2220364 | [6 empty] | 128891 |  |  | 8.14 | 8.6 | 10 | 9.48 | 72% | 66.57% |  |  | 26 | 21
GTAL | 23812 | 48509 | 175085 | [6 empty] | 42890 |  |  | 7.67 | 5.6 | 10 | 8 | 63% | 11.72% |  |  | 26 | 21
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 109045 | 3461205 | 2718890 | [6 empty] | 103409 |  |  | 4.22 | 3.82 | 10 | 9.98 | 80% | 74.94% |  |  | 26 | 21
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-