## Sheet1
Plan vs Achievement
Date: | 27-Nov-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 97525 | 2203539 | 1904795 | [6 empty] | 97758 |  |  | 7.6 | 7.84 | 10 | 10.48 | 72% | 70.68% |  |  | 26 | 24
JAL3 | 14190 | 313636 | 286696 | [6 empty] | 13170 |  |  | 6.47 | 6.56 | 10 | 10.98 | 72% | 72.77% |  |  | 26 | 24
JFL | 45243 | 1498277 | 976778 | [6 empty] | 44889 |  |  | 6.49 | 6.35 | 10 | 9.22 | 73% | 67.87% |  |  | 26 | 24
JKL | 79358 | 2014480 | 1356596 | [6 empty] | 88472 |  |  | 9.27 | 9.36 | 10 | 8.94 | 65% | 57.46% |  |  | 26 | 24
MFL | 69348 | 2332178 | 1733983 | [6 empty] | 77622 |  |  | 7.82 | 7.52 | 10 | 9.28 | 72% | 67.31% |  |  | 26 | 24
FFL2 | 101730 | 2597126 | 2254511 | [6 empty] | 101555 |  |  | 7.34 | 7.18 | 10 | 11.83 | 73% | 68.64% |  |  | 26 | 24
JKL-U2 | 128791 | 3823698 | 2605546 | [6 empty] | 141287 |  |  | 8.14 | 8.42 | 10 | 9.53 | 72% | 66.52% |  |  | 26 | 24
GTAL | 34600 | 48509 | 273007 | [6 empty] | 55618 |  |  | 7.67 | 5.33 | 10 | 8.09 | 63% | 15.1% |  |  | 26 | 24
GMT TOTAL: | [12 empty] | 7.82 |  | 10 |  | 71.51% |  |  |  | 26
LINGERIE | 115630 | 3461205 | 3035180 | [6 empty] | 112505 |  |  | 4.22 | 3.83 | 10 | 9.81 | 80% | 74.64% |  |  | 26 | 24
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-