## Sheet1
Plan vs Achievement
Date: | 03-Dec-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 94378 | 2746419 | 285379 | [6 empty] | 94456 |  |  | 7.05 | 6.66 | 10 | 10.09 | 70% | 73.95% |  |  | 26 | 3
JAL3 | 11115 | 350940 | 37930 | [6 empty] | 10284 |  |  | 7.05 | 6.31 | 10 | 11.59 | 70% | 74.02% |  |  | 26 | 3
JFL | 43662 | 1530868 | 126102 | [6 empty] | 39431 |  |  | 6.78 | 7.56 | 11 | 11.29 | 74% | 66.64% |  |  | 26 | 3
JKL | 73582 | 2273631 | 217175 | [6 empty] | 83543 |  |  | 8.41 | 8.32 | 10 | 9.38 | 63% | 59.88% |  |  | 26 | 3
MFL | 71222 | 2343006 | 213499 | [6 empty] | 76491 |  |  | 7.38 | 7.05 | 10 | 8.87 | 71% | 66.46% |  |  | 26 | 3
FFL2 | 110958 | 2907274 | 329970 | [6 empty] | 111061 |  |  | 6.53 | 5.93 | 10 | 10.55 | 68% | 74.38% |  |  | 26 | 3
JKL-U2 | 131966 | 3971692 | 383389 | [6 empty] | 140680 |  |  | 7.9 | 7.33 | 10 | 9.49 | 68% | 67.52% |  |  | 26 | 3
GTAL | 44692 | 0 | 131038 | [6 empty] | 68468 |  |  | 0 | 4.66 | 10 | 10.55 | 63% | 44.42% |  |  | 26 | 3
GMT TOTAL: | [12 empty] | 7.38 |  | 10 |  | 68.63% |  |  |  | 26
LINGERIE | 136789 | 3336726 | 391959 | [6 empty] | 122871 |  |  | 4.19 | 3.78 | 10.08 | 10.19 | 79% | 73.69% |  |  | 26 | 3
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-