## Sheet1
Plan vs Achievement
Date: | 08-Dec-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 94610 | 3046419 | 685163 | [6 empty] | 92974 |  |  | 7.05 | 6.69 | 10 | 10.5 | 70% | 73.7% |  |  | 26 | 7
JAL3 | 11980 | 350940 | 87190 | [6 empty] | 7191 |  |  | 7.05 | 6.11 | 10 | 11.16 | 70% | 74.7% |  |  | 26 | 7
JFL | 47698 | 1530868 | 327352 | [6 empty] | 45990 |  |  | 6.78 | 6.58 | 11 | 10.71 | 74% | 69.47% |  |  | 26 | 7
JKL | 74625 | 2273631 | 521617 | [6 empty] | 79817 |  |  | 8.41 | 8.22 | 10 | 9.58 | 63% | 61.05% |  |  | 26 | 7
MFL | 60968 | 2343006 | 470398 | [6 empty] | 67760 |  |  | 7.38 | 7.28 | 10 | 8.58 | 71% | 66.51% |  |  | 26 | 7
FFL2 | 114993 | 2907274 | 773726 | [6 empty] | 118125 |  |  | 6.53 | 5.89 | 10 | 10.84 | 68% | 72.35% |  |  | 26 | 7
JKL-U2 | 127126 | 3971692 | 902458 | [6 empty] | 130571 |  |  | 7.9 | 7.32 | 10 | 9.48 | 68% | 68.79% |  |  | 26 | 7
GTAL | 45751 | 0 | 321985 | [6 empty] | 67520 |  |  | 0 | 4.67 | 10 | 11.08 | 63% | 46.92% |  |  | 26 | 7
GMT TOTAL: | [12 empty] | 7.38 |  | 10 |  | 68.63% |  |  |  | 26
LINGERIE | 135710 | 3336726 | 945260 | [6 empty] | 118561 |  |  | 4.19 | 3.77 | 10.08 | 10.26 | 79% | 75.29% |  |  | 26 | 7
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-