## Sheet1
Plan vs Achievement
Date: | 09-Dec-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 93848 | 3046419 | 779011 | [6 empty] | 95765 |  |  | 7.05 | 6.77 | 10 | 10.66 | 70% | 73.58% |  |  | 26 | 8
JAL3 | 12155 | 350940 | 99345 | [6 empty] | 7768 |  |  | 7.05 | 6.1 | 10 | 11.14 | 70% | 74.88% |  |  | 26 | 8
JFL | 48390 | 1530868 | 375742 | [6 empty] | 47068 |  |  | 6.78 | 6.5 | 11 | 10.65 | 74% | 69.63% |  |  | 26 | 8
JKL | 79966 | 2273631 | 601583 | [6 empty] | 89170 |  |  | 8.41 | 8.14 | 10 | 9.63 | 63% | 61.02% |  |  | 26 | 8
MFL | 60508 | 2343006 | 530906 | [6 empty] | 67065 |  |  | 7.38 | 7.32 | 10 | 8.56 | 71% | 66.37% |  |  | 26 | 8
FFL2 | 114566 | 2907274 | 888292 | [6 empty] | 120512 |  |  | 6.53 | 5.89 | 10 | 10.95 | 68% | 72.04% |  |  | 26 | 8
JKL-U2 | 125430 | 3971692 | 1028188 | [6 empty] | 128365 |  |  | 7.9 | 7.36 | 10 | 9.5 | 68% | 68.87% |  |  | 26 | 8
GTAL | 38992 | 0 | 360977 | [6 empty] | 57354 |  |  | 0 | 4.68 | 10 | 10.96 | 63% | 46.97% |  |  | 26 | 8
GMT TOTAL: | [12 empty] | 7.38 |  | 10 |  | 68.63% |  |  |  | 26
LINGERIE | 140812 | 3336726 | 1086072 | [6 empty] | 125878 |  |  | 4.19 | 3.76 | 10.08 | 10.3 | 79% | 75.43% |  |  | 26 | 8
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-