## Sheet1
Plan vs Achievement
Date: | 11-Dec-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 93262 | 3046419 | 966383 | [6 empty] | 91255 |  |  | 7.05 | 6.92 | 10 | 10.91 | 70% | 73.28% |  |  | 26 | 10
JAL3 | 15505 | 350940 | 127925 | [6 empty] | 9989 |  |  | 7.05 | 6.05 | 10 | 11.45 | 70% | 74.9% |  |  | 26 | 10
JFL | 48348 | 1530868 | 471987 | [6 empty] | 48880 |  |  | 6.78 | 6.32 | 11 | 10.47 | 74% | 69.96% |  |  | 26 | 10
JKL | 77582 | 2273631 | 763850 | [6 empty] | 92091 |  |  | 8.41 | 8.01 | 10 | 9.7 | 63% | 60.97% |  |  | 26 | 10
MFL | 66261 | 2343006 | 657916 | [6 empty] | 71686 |  |  | 7.38 | 7.32 | 10 | 8.56 | 71% | 66.36% |  |  | 26 | 10
FFL2 | 118116 | 2907274 | 1125851 | [6 empty] | 121308 |  |  | 6.53 | 5.88 | 10 | 11.2 | 68% | 71.9% |  |  | 26 | 10
JKL-U2 | 135183 | 3971692 | 1297735 | [6 empty] | 147895 |  |  | 7.9 | 7.41 | 10 | 9.67 | 68% | 69.09% |  |  | 26 | 10
GTAL | 33563 | 0 | 429480 | [6 empty] | 57264 |  |  | 0 | 4.7 | 10 | 10.79 | 63% | 45.93% |  |  | 26 | 10
GMT TOTAL: | [12 empty] | 7.38 |  | 10 |  | 68.63% |  |  |  | 26
LINGERIE | 109060 | 3336726 | 1323167 | [6 empty] | 103415 |  |  | 4.19 | 3.77 | 10.08 | 10.17 | 79% | 75.17% |  |  | 26 | 10
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-