## Sheet1
Plan vs Achievement
Date: | 17-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 77850 | 2143885 | 1308980 | [6 empty] | 77751 |  |  | 7.53 | 7.02 | 10 | 10.56 | 67% | 67.7% |  |  | 27 | 15
JAL3 | 8320 | 262272 | 169430 | [6 empty] | 8542 |  |  | 6.08 | 5.94 | 10 | 10.11 | 66% | 72.89% |  |  | 27 | 15
JFL | 61878 | 1913112 | 887378 | [6 empty] | 62374 |  |  | 6.24 | 6.46 | 11 | 13.11 | 72.8% | 67.26% |  |  | 27 | 15
JKL | 89539 | 2200195 | 1327246 | [6 empty] | 96081 |  |  | 8.75 | 8.65 | 9 | 11.37 | 64.2% | 66.48% |  |  | 27 | 15
MFL | 73437 | 2146320 | 1020333 | [6 empty] | 88379 |  |  | 7.37 | 6.99 | 10 | 9.03 | 66.2% | 62.38% |  |  | 27 | 15
FFL2 | 88420 | 2342283 | 1406585 | [6 empty] | 102596 |  |  | 8.17 | 7.43 | 10 | 12.97 | 68% | 61.59% |  |  | 27 | 15
JKL-U2 | 108472 | 3425817 | 1683266 | [6 empty] | 126571 |  |  | 9.31 | 9.21 | 10 | 11.36 | 65% | 63.25% |  |  | 27 | 15
GMT TOTAL: | 507916 |  | 7803218 | [6 empty] | 562293.94 |  |  | 7.97 | 7.75 | 9.98 | 11.18 | 67% | 64.59% |  |  | 27 | 15
LINGERIE | 132510 | 3336041 | 2074512 | [6 empty] | 132863 |  |  | 3.59 | 3.62 | 9 | 9.99 | 78% | 74.41% |  |  | 27 | 15
GTAL | 27630 | 959072 | 576287 | [6 empty] | 42945 |  |  | 6.82 | 6.04 | 10 | 11.46 | 61.8% | 41.94% |  |  | 27 | 15
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-