## Sheet1
Plan vs Achievement
Date: | 22-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 87625 | 2143885 | 1639337 | [6 empty] | 86665 |  |  | 7.53 | 7.18 | 10 | 10.73 | 67% | 66.73% |  |  | 27 | 19
JAL3 | 11140 | 262272 | 208460 | [6 empty] | 11311 |  |  | 6.08 | 5.96 | 10 | 9.91 | 66% | 72.84% |  |  | 27 | 19
JFL | 55324 | 1913112 | 1135832 | [6 empty] | 54980 |  |  | 6.24 | 6.41 | 11 | 12.89 | 72.8% | 67.57% |  |  | 27 | 19
JKL | 85987 | 2200195 | 1685810 | [6 empty] | 93349 |  |  | 8.75 | 8.54 | 9 | 11.11 | 64.2% | 67.22% |  |  | 27 | 19
MFL | 72690 | 2146320 | 1313195 | [6 empty] | 90313 |  |  | 7.37 | 6.87 | 10 | 9.02 | 66.2% | 62.01% |  |  | 27 | 19
FFL2 | 73440 | 2342283 | 1721822 | [6 empty] | 84747 |  |  | 8.17 | 7.57 | 10 | 12.79 | 68% | 61.5% |  |  | 27 | 19
JKL-U2 | 120152 | 3425817 | 2209724 | [6 empty] | 136838 |  |  | 9.31 | 9.19 | 10 | 11.49 | 65% | 63.1% |  |  | 27 | 19
GMT TOTAL: | 506358 |  | 9914180 | [6 empty] | 558201.8 |  |  | 7.97 | 7.77 | 9.98 | 11.12 | 67% | 64.5% |  |  | 27 | 19
LINGERIE | 128960 | 3336041 | 2627402 | [6 empty] | 141890 |  |  | 3.59 | 3.61 | 9 | 9.99 | 78% | 73.49% |  |  | 27 | 19
GTAL | 21617 | 959072 | 710315 | [6 empty] | 23705 |  |  | 6.82 | 5.86 | 10 | 10.63 | 61.8% | 42.07% |  |  | 27 | 19
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-