## Sheet1
Plan vs Achievement
Date: | 28-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 71795 | 2143885 | 1996555 | [6 empty] | 77584 |  |  | 7.53 | 7.5 | 10 | 10.82 | 67% | 66.6% |  |  | 27 | 24
JAL3 | 10805 | 262272 | 259190 | [6 empty] | 11408 |  |  | 6.08 | 6 | 10 | 9.71 | 66% | 73.18% |  |  | 27 | 24
JFL | 45724 | 1913112 | 1373764 | [6 empty] | 45372 |  |  | 6.24 | 6.51 | 11 | 12.45 | 72.8% | 67.76% |  |  | 27 | 24
JKL | 91306 | 2200195 | 2155339 | [6 empty] | 97544 |  |  | 8.75 | 8.52 | 9 | 11.06 | 64.2% | 67.55% |  |  | 27 | 24
MFL | 66944 | 2146320 | 1648125 | [6 empty] | 80388 |  |  | 7.37 | 6.9 | 10 | 8.99 | 66.2% | 61.98% |  |  | 27 | 24
FFL2 | 64270 | 2342283 | 2083718 | [6 empty] | 71143 |  |  | 8.17 | 7.72 | 10 | 12.43 | 68% | 61.7% |  |  | 27 | 24
JKL-U2 | 98891 | 3425817 | 2786167 | [6 empty] | 116490 |  |  | 9.31 | 9.21 | 10 | 11.46 | 65% | 62.18% |  |  | 27 | 24
GMT TOTAL: | 449735 |  | 12302858 | [6 empty] | 499930.22 |  |  | 7.97 | 7.88 | 9.98 | 11.02 | 67% | 64.35% |  |  | 27 | 24
LINGERIE | 137680 | 3336041 | 3282663 | [6 empty] | 127568 |  |  | 3.59 | 3.6 | 9 | 9.95 | 78% | 73.2% |  |  | 27 | 24
GTAL | 25896 | 959072 | 859184 | [6 empty] | 30456 |  |  | 6.82 | 5.87 | 10 | 10.41 | 61.8% | 41.2% |  |  | 27 | 24
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-