## Sheet1
Plan vs Achievement
Date: | 29-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 76593 | 2221275 | 2073148 | [6 empty] | 78565 |  |  | 7.53 | 7.54 | 10 | 10.85 | 67% | 66.57% |  |  | 27 | 25
JAL3 | 9345 | 277752 | 268535 | [6 empty] | 9763 |  |  | 6.08 | 6.01 | 10 | 9.64 | 66% | 73.26% |  |  | 27 | 25
JFL | 48005 | 1517636 | 1421769 | [6 empty] | 47352 |  |  | 6.24 | 6.5 | 11 | 12.35 | 72.8% | 67.85% |  |  | 27 | 25
JKL | 91197 | 2407339 | 2246536 | [6 empty] | 96634 |  |  | 8.75 | 8.52 | 9 | 11.02 | 64.2% | 67.7% |  |  | 27 | 25
MFL | 64510 | 1845596 | 1712635 | [6 empty] | 79645 |  |  | 7.37 | 6.9 | 10 | 8.98 | 66.2% | 61.87% |  |  | 27 | 25
FFL2 | 65215 | 2295280 | 2148933 | [6 empty] | 68946 |  |  | 8.17 | 7.74 | 10 | 12.3 | 68% | 61.78% |  |  | 27 | 25
JKL-U2 | 89939 | 3140186 | 2878891 | [6 empty] | 110276 |  |  | 9.31 | 9.22 | 10 | 11.39 | 65% | 62.11% |  |  | 27 | 25
GMT TOTAL: | 444804 |  | 12750447 | [6 empty] | 491180.18 |  |  | 7.97 | 7.89 | 9.98 | 10.97 | 67% | 64.36% |  |  | 27 | 25
LINGERIE | 133810 | 3615050 | 3416473 | [6 empty] | 129343 |  |  | 3.59 | 3.6 | 9 | 9.95 | 78% | 73.27% |  |  | 27 | 25
GTAL | 20948 | 880498 | 880464 | [6 empty] | 27411 |  |  | 6.82 | 5.9 | 10 | 10.31 | 61.8% | 40.97% |  |  | 27 | 25
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-