## Sheet1
Plan vs Achievement
Date: | 09-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 80025 | 2143885 | 727310 | 1416575 | 635225.1852 | -92084.8148 | 74830 | 563469.9 | 581781.75 | 84666 | 110.5% | 7483 | 7.53 | 7.27 | 10 | 11.05 | 67% | 68.37% | 5287543.7 | 4783245.6444 | 27 | 8 | 19
JAL3 | 10100 | 262272 | 93230 | 169042 | 77710.2222 | -15519.7778 | 8957.1 | 54459.168 | 60398 | 10730 | 118% | 895.71 | 6.08 | 5.98 | 10 | 10.21 | 66% | 72.37% | 557515.4 | 472478.1511 | 27 | 8 | 19
JFL | 63922 | 1913112 | 479940 | 1433172 | 566848 | 86908 | 74854.7 | 467093.328 | 414214.56 | 70050 | 87.92% | 6804.9727 | 6.24 | 6.48 | 11 | 13.44 | 72.8% | 66.86% | 3110011.2 | 3537131.52 | 27 | 8 | 19
JKL | 84120 | 2200195 | 699696 | 1500499 | 651909.6296 | -47786.3704 | 79230.95 | 693270.8125 | 745303.2 | 92109 | 108.7% | 8803.4389 | 8.75 | 8.86 | 9 | 11.49 | 64.2% | 66.29% | 6199306.56 | 5704209.2593 | 27 | 8 | 19
MFL | 63985 | 2146320 | 542877 | 1603443 | 635946.6667 | 93069.6667 | 83371.4 | 614447.218 | 456852.9 | 75572 | 82.7% | 8337.14 | 7.37 | 7.14 | 10 | 9.17 | 66.2% | 63.25% | 3876141.78 | 4686926.9333 | 27 | 8 | 19
FFL2 | 99594 | 2342283 | 808883 | 1533400 | 694009.7778 | -114873.2222 | 81649.7 | 667078.049 | 719068.68 | 118417 | 103% | 8164.97 | 8.17 | 7.22 | 10 | 13.22 | 68% | 62.35% | 5840135.26 | 5670059.8844 | 27 | 8 | 19
JKL-U2 | 113486 | 3425817 | 852169 | 2573648 | 1015056.8889 | 162887.8889 | 134356.7 | 1250860.877 | 1065633.54 | 132699 | 84.67% | 13435.67 | 9.31 | 9.39 | 10 | 11.23 | 65% | 63.54% | 8001866.91 | 9450179.6356 | 27 | 8 | 19
GMT TOTAL: | 515232 | 14433884 | 4204105 | 10229779 | 4276706.3704 | 72601.3704 | 537250.55 | 4281886.8835 | 4029114.24 | 584243.22 | 96.45% | 53832.7204 | 7.97 | 7.82 | 9.98 | 11.36 | 67% | 64.97% | 32876101.1 | 34085349.7719 | 27 | 8 | 19
LINGERIE | 132240 | 3336041 | 1082968 | 2253073 | 988456.5926 | -94511.4074 | 119265.65 | 428163.6835 | 487965.6 | 128783 | 112.6% | 13251.7389 | 3.59 | 3.69 | 9 | 9.83 | 78% | 74.98% | 3996151.92 | 3548559.1674 | 27 | 8 | 19
GTAL | 42424 | 959072 | 319833 | 639239 | 284169.4815 | -35663.5185 | 34083.15 | 232447.083 | 263877.28 | 77177 | 102.6% | 3408.315 | 6.82 | 6.22 | 10 | 11.19 | 61.8% | 41.75% | 1989361.26 | 1938035.8637 | 27 | 8 | 19
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
14433884 | 4204105 | 510000 | 9690000 | 13894105 | 539779
- |  | 545000 | 10355000 | 14559105 | -125221
- |  | 580000 | 11020000 | 15224105 | -790221
- |  | 615000 | 11685000 | 15889105 | -1455221
- |  | 650000 | 12350000 | 16554105 | -2120221
- |  | 685000 | 13015000 | 17219105 | -2785221