## Sheet1
Plan vs Achievement
Date: | 10-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 86995 | 2143885 | 814305 | [6 empty] | 90580 |  |  | 7.53 | 7.24 | 10 | 11.02 | 67% | 68.33% |  |  | 27 | 10
JAL3 | 14095 | 262272 | 107325 | [6 empty] | 14309 |  |  | 6.08 | 5.97 | 10 | 10.53 | 66% | 72.47% |  |  | 27 | 10
JFL | 57445 | 1913112 | 537385 | [6 empty] | 60962 |  |  | 6.24 | 6.5 | 11 | 13.51 | 72.8% | 66.71% |  |  | 27 | 10
JKL | 91191 | 2200195 | 790887 | [6 empty] | 98672 |  |  | 8.75 | 8.8 | 9 | 11.58 | 64.2% | 66.04% |  |  | 27 | 10
MFL | 61897 | 2146320 | 604774 | [6 empty] | 73637 |  |  | 7.37 | 7.15 | 10 | 9.13 | 66.2% | 63.07% |  |  | 27 | 10
FFL2 | 93575 | 2342283 | 902458 | [6 empty] | 108412 |  |  | 8.17 | 7.26 | 10 | 13.22 | 68% | 62.42% |  |  | 27 | 10
JKL-U2 | 106932 | 3425817 | 959991 | [6 empty] | 124419 |  |  | 9.31 | 9.37 | 10 | 11.24 | 65% | 63.63% |  |  | 27 | 10
GMT TOTAL: | 512130 |  | 4717125 | [6 empty] | 570990.32 |  |  | 7.97 | 7.82 | 9.98 | 11.38 | 67% | 64.92% |  |  | 27 | 10
LINGERIE | 139220 | 3336041 | 1222188 | [6 empty] | 136189 |  |  | 3.59 | 3.69 | 9 | 9.85 | 78% | 75.05% |  |  | 27 | 10
GTAL | 40462 | 959072 | 362445 | [6 empty] | 67701 |  |  | 6.82 | 6.22 | 10 | 11.39 | 61.8% | 42.66% |  |  | 27 | 10
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-