## Sheet1
Plan vs Achievement
Date: | 16-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 79473 | 2143885 | 1231130 | [6 empty] | 79703 |  |  | 7.53 | 7.03 | 10 | 10.6 | 67% | 67.94% |  |  | 27 | 14
JAL3 | 11210 | 262272 | 161110 | [6 empty] | 9443 |  |  | 6.08 | 5.94 | 10 | 10.28 | 66% | 72.82% |  |  | 27 | 14
JFL | 61864 | 1913112 | 825500 | [6 empty] | 65162 |  |  | 6.24 | 6.5 | 11 | 13.15 | 72.8% | 67.3% |  |  | 27 | 14
JKL | 88864 | 2200195 | 1237707 | [6 empty] | 96086 |  |  | 8.75 | 8.67 | 9 | 11.43 | 64.2% | 66.33% |  |  | 27 | 14
MFL | 72346 | 2146320 | 946896 | [6 empty] | 86372 |  |  | 7.37 | 7.04 | 10 | 9.05 | 66.2% | 62.37% |  |  | 27 | 14
FFL2 | 86442 | 2342283 | 1318165 | [6 empty] | 97421 |  |  | 8.17 | 7.39 | 10 | 12.94 | 68% | 61.64% |  |  | 27 | 14
JKL-U2 | 116740 | 3425817 | 1573094 | [6 empty] | 137027 |  |  | 9.31 | 9.24 | 10 | 11.38 | 65% | 63.22% |  |  | 27 | 14
GMT TOTAL: | 516939 |  | 7293602 | [6 empty] | 571212.81 |  |  | 7.97 | 7.77 | 9.98 | 11.21 | 67% | 64.61% |  |  | 27 | 14
LINGERIE | 145914 | 3336041 | 1942026 | [6 empty] | 149505 |  |  | 3.59 | 3.62 | 9 | 10.02 | 78% | 74.39% |  |  | 27 | 14
GTAL | 24788 | 959072 | 545502 | [6 empty] | 50610 |  |  | 6.82 | 6 | 10 | 11.12 | 61.8% | 42.75% |  |  | 27 | 14
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-