## Sheet1
Plan vs Achievement
Date: | 01-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 91380 | 2143885 | 91380 | [6 empty] | 94942 |  |  | 7.53 | 7.35 | 10 | 11.51 | 67% | 67.25% |  |  | 27 | 1
JAL3 | 11655 | 262272 | 11655 | [6 empty] | 12805 |  |  | 6.08 | 6.3 | 10 | 11.15 | 66% | 70.96% |  |  | 27 | 1
JFL | 61785 | 1913112 | 61785 | [6 empty] | 66613 |  |  | 6.24 | 6.1 | 11 | 13.71 | 72.8% | 63.25% |  |  | 27 | 1
JKL | 89869 | 2200195 | 89869 | [6 empty] | 97576 |  |  | 8.75 | 9.36 | 9 | 12.28 | 64.2% | 65.72% |  |  | 27 | 1
MFL | 68942 | 2146320 | 68942 | [6 empty] | 80141 |  |  | 7.37 | 7.13 | 10 | 8.76 | 66.2% | 64.67% |  |  | 27 | 1
FFL2 | 107353 | 2342283 | 107353 | [6 empty] | 121643 |  |  | 8.17 | 6.85 | 10 | 13.5 | 68% | 62.26% |  |  | 27 | 1
JKL-U2 | 102396 | 3425817 | 102396 | [6 empty] | 115804 |  |  | 9.31 | 9.35 | 10 | 9.96 | 65% | 66% |  |  | 27 | 1
GMT TOTAL: | 533380 |  | 533380 | [6 empty] | 589523.32 |  |  | 7.97 | 7.77 | 9.98 | 11.41 | 67% | 65.11% |  |  | 27 | 1
LINGERIE | 136678 | 3336041 | 136678 | [6 empty] | 128905 |  |  | 3.59 | 3.64 | 9 | 9.48 | 78% | 77.73% |  |  | 27 | 1
GTAL-RMG | 16511 | 959072 | 16511 | [6 empty] | 33271 |  |  | 6.82 | 6.34 | 10 | 9.52 | 61.8% | 35.23% |  |  | 27 | 1
GTAL-LIN | 16081 | 0 | 16081 | [6 empty] | 20801 |  |  | 0 | 5.27 | 0 | 9.25 | 0% | 50.99% |  |  | 27 | 1
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-