## Sheet1
Plan vs Achievement
Date: | 03-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 90634 | 2143885 | 273939 | [6 empty] | 95680 |  |  | 7.53 | 7.39 | 10 | 11.57 | 67% | 68.03% |  |  | 27 | 3
JAL3 | 11955 | 262272 | 35485 | [6 empty] | 11653 |  |  | 6.08 | 6.09 | 10 | 11.21 | 66% | 71.88% |  |  | 27 | 3
JFL | 55221 | 1913112 | 175484 | [6 empty] | 61184 |  |  | 6.24 | 6.18 | 11 | 13.49 | 72.8% | 64.24% |  |  | 27 | 3
JKL | 85955 | 2200195 | 260773 | [6 empty] | 95680 |  |  | 8.75 | 9.21 | 9 | 12.07 | 64.2% | 64.77% |  |  | 27 | 3
MFL | 61268 | 2146320 | 194496 | [6 empty] | 72665 |  |  | 7.37 | 7.41 | 10 | 8.66 | 66.2% | 64.95% |  |  | 27 | 3
FFL2 | 90467 | 2342283 | 303563 | [6 empty] | 106387 |  |  | 8.17 | 6.92 | 10 | 13.05 | 68% | 62.26% |  |  | 27 | 3
JKL-U2 | 104543 | 3425817 | 303125 | [6 empty] | 117446 |  |  | 9.31 | 9.44 | 10 | 10.59 | 65% | 64% |  |  | 27 | 3
GMT TOTAL: | 500043 |  | 1546865 | [6 empty] | 560694.37 |  |  | 7.97 | 7.84 | 9.98 | 11.38 | 67% | 64.74% |  |  | 27 | 3
LINGERIE | 141440 | 3336041 | 412088 | [6 empty] | 138537 |  |  | 3.59 | 3.62 | 9 | 9.77 | 78% | 75.71% |  |  | 27 | 3
GTAL-RMG | 17514 | 959072 | 52791 | [6 empty] | 33463 |  |  | 6.82 | 6.02 | 10 | 9.05 | 61.8% | 36.15% |  |  | 27 | 3
GTAL-LIN | 14774 | 0 | 49219 | [6 empty] | 24525 |  |  | 0 | 5.34 | 0 | 11.02 | 0% | 44.84% |  |  | 27 | 3
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-