## Sheet1
Plan vs Achievement
Date: | 05-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 92310 | 2143885 | 388487 | [6 empty] | 94314 |  |  | 7.53 | 7.34 | 10 | 11.55 | 67% | 68.44% |  |  | 27 | 4
JAL3 | 10350 | 262272 | 50315 | [6 empty] | 10336 |  |  | 6.08 | 6.06 | 10 | 10.77 | 66% | 73.08% |  |  | 27 | 4
JFL | 51319 | 1913112 | 242186 | [6 empty] | 50329 |  |  | 6.24 | 6.39 | 11 | 13.43 | 72.8% | 64.88% |  |  | 27 | 4
JKL | 89881 | 2200195 | 351076 | [6 empty] | 98558 |  |  | 8.75 | 9.06 | 9 | 11.81 | 64.2% | 65.72% |  |  | 27 | 4
MFL | 69643 | 2146320 | 264139 | [6 empty] | 79566 |  |  | 7.37 | 7.38 | 10 | 8.87 | 66.2% | 64.68% |  |  | 27 | 4
FFL2 | 100258 | 2342283 | 427185 | [6 empty] | 120456 |  |  | 8.17 | 6.99 | 10 | 13.19 | 68% | 61.94% |  |  | 27 | 4
JKL-U2 | 106944 | 3425817 | 410069 | [6 empty] | 120416 |  |  | 9.31 | 9.45 | 10 | 10.88 | 65% | 63.54% |  |  | 27 | 4
GMT TOTAL: | 520705 |  | 2133457 | [6 empty] | 573975.48 |  |  | 7.97 | 7.83 | 9.98 | 11.41 | 67% | 64.86% |  |  | 27 | 4
LINGERIE | 142180 | 3336041 | 557528 | [6 empty] | 142412 |  |  | 3.59 | 3.65 | 9 | 9.92 | 78% | 75.2% |  |  | 27 | 4
GTAL-RMG | 16015 | 959072 | 77276 | [6 empty] | 32733 |  |  | 6.82 | 6.26 | 10 | 8.84 | 61.8% | 36.58% |  |  | 27 | 4
GTAL-LIN | 18062 | 0 | 77131 | [6 empty] | 26614 |  |  | 0 | 5.74 | 0 | 11.77 | 0% | 46.92% |  |  | 27 | 4
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-