## Sheet1
Plan vs Achievement
Date: | 07-Jul-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 87416 | 2143885 | 565555 | 1578330 | 476418.8889 | -89136.1111 | 75715.7273 | 570139.4264 | 639885.12 | 92344 | 115.4% | 7571.5727 | 7.53 | 7.32 | 10 | 11.38 | 67% | 68.38% | 4139862.6 | 3587434.2333 | 27 | 6 | 21
JAL3 | 10540 | 262272 | 72360 | 189912 | 58282.6667 | -14077.3333 | 9111.4545 | 55397.6436 | 63450.8 | 10377 | 122.9% | 911.1455 | 6.08 | 6.02 | 10 | 10.43 | 66% | 73.28% | 435607.2 | 354358.6133 | 27 | 6 | 21
JFL | 56797 | 1913112 | 354863 | 1558249 | 425136 | 70273 | 73411.1818 | 458085.7745 | 373724.26 | 58562 | 88.02% | 6673.7438 | 6.24 | 6.58 | 11 | 13.44 | 72.8% | 66.33% | 2334998.54 | 2652848.64 | 27 | 6 | 21
JKL | 87991 | 2200195 | 531763 | 1668432 | 488932.2222 | -42830.7778 | 79837.4091 | 698577.3295 | 783999.81 | 94899 | 110.7% | 8870.8232 | 8.75 | 8.91 | 9 | 11.57 | 64.2% | 66.88% | 4738008.33 | 4278156.9444 | 27 | 6 | 21
MFL | 69033 | 2146320 | 406031 | 1740289 | 476960 | 70929 | 82241.9091 | 606122.87 | 501869.91 | 79020 | 83.97% | 8224.1909 | 7.37 | 7.27 | 10 | 9.14 | 66.2% | 63.83% | 2951845.37 | 3515195.2 | 27 | 6 | 21
FFL2 | 84668 | 2342283 | 609581 | 1732702 | 520507.3333 | -89073.6667 | 82607.7273 | 674905.1318 | 603682.84 | 96869 | 102.2% | 8260.7727 | 8.17 | 7.13 | 10 | 13.11 | 68% | 61.88% | 4346312.53 | 4252544.9133 | 27 | 6 | 21
JKL-U2 | 114176 | 3425817 | 627870 | 2797947 | 761292.6667 | 133422.6667 | 132369.2273 | 1232357.5059 | 1073254.4 | 132117 | 83.27% | 13236.9227 | 9.31 | 9.4 | 10 | 11.11 | 65% | 63.1% | 5901978 | 7087634.7267 | 27 | 6 | 21
GMT TOTAL: | 510621 | 14433884 | 3168023 | 11265861 | 3207529.7778 | 39506.7778 | 535294.6364 | 4266298.2518 | 4003268.64 | 564188.98 | 97.16% | 53636.7371 | 7.97 | 7.84 | 9.98 | 11.39 | 67% | 64.96% | 24837300.32 | 25564012.3289 | 27 | 6 | 21
LINGERIE | 132460 | 3336041 | 819508 | 2516533 | 741342.4444 | -78165.5556 | 120408.7727 | 432267.4941 | 487452.8 | 134246 | 113.3% | 13378.7525 | 3.59 | 3.68 | 9 | 9.82 | 78% | 74.83% | 3015789.44 | 2661419.3756 | 27 | 6 | 21
GTAL | 37010 | 959072 | 231631 | 727441 | 213127.1111 | -18503.8889 | 34747.7727 | 236979.81 | 231682.6 | 61748 | 99.76% | 3474.7773 | 6.82 | 6.26 | 10 | 6.44 | 61.8% | 43.65% | 1450010.06 | 1453526.8978 | 27 | 6 | 21
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
14433884 | 3168023 | 510000 | 10710000 | 13878023 | 555861
- |  | 545000 | 11445000 | 14613023 | -179139
- |  | 580000 | 12180000 | 15348023 | -914139
- |  | 615000 | 12915000 | 16083023 | -1649139
- |  | 650000 | 13650000 | 16818023 | -2384139
- |  | 685000 | 14385000 | 17553023 | -3119139