## Sheet1
Plan vs Achievement
Date: | 04-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 64850 | 2061190 | 261308 | [6 empty] | 64105 |  |  | 6.87 | 8.51 | 10 | 9.2 | 68% | 70.58% |  |  | 25 | 4
JAL3 | 9290 | 252869 | 37425 | [6 empty] | 9283 |  |  | 6.44 | 6.89 | 10 | 9.15 | 66% | 72.92% |  |  | 25 | 4
JFL | 39383 | 1022653 | 168901 | [6 empty] | 33618 |  |  | 6.51 | 6.58 | 8 | 8.05 | 71.8% | 78.24% |  |  | 25 | 4
JKL | 63140 | 1740159 | 259114 | [6 empty] | 68571 |  |  | 10.12 | 8.84 | 9 | 8.89 | 58.8% | 62.49% |  |  | 25 | 4
MFL | 74056 | 2149237 | 288277 | [6 empty] | 79432 |  |  | 7.36 | 7.46 | 10 | 9.09 | 64% | 67.33% |  |  | 25 | 4
FFL2 | 75440 | 2425855 | 284165 | [6 empty] | 73975 |  |  | 6.62 | 7.14 | 10 | 8.65 | 68% | 67.97% |  |  | 25 | 4
JKL-U2 | 92356 | 2998611 | 376687 | [6 empty] | 95757 |  |  | 8.92 | 9.04 | 10 | 8.41 | 65% | 67.69% |  |  | 25 | 4
GTAL | 63 | 6632 | 6221 | [6 empty] | 1606 |  |  | 9.11 | 3.01 | 8 | 8.09 | 63% | 2.9% |  |  | 25 | 4
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 109740 | 3797404 | 452772 | [6 empty] | 107834 |  |  | 4.06 | 3.96 | 11 | 9.34 | 78% | 71.97% |  |  | 25 | 4
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-