## Sheet1
Plan vs Achievement
Date: | 08-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 71472 | 2061190 | 390026 | [6 empty] | 72376 |  |  | 6.87 | 8.59 | 10 | 9.23 | 68% | 70.86% |  |  | 25 | 6
JAL3 | 9210 | 252869 | 54355 | [6 empty] | 9823 |  |  | 6.44 | 6.92 | 10 | 9.14 | 66% | 72.79% |  |  | 25 | 6
JFL | 40585 | 1022653 | 249255 | [6 empty] | 36103 |  |  | 6.51 | 6.64 | 8 | 8.16 | 71.8% | 77.8% |  |  | 25 | 6
JKL | 65088 | 1740159 | 391999 | [6 empty] | 77163 |  |  | 10.12 | 9 | 9 | 9.35 | 58.8% | 62.26% |  |  | 25 | 6
MFL | 75182 | 2149237 | 437456 | [6 empty] | 81974 |  |  | 7.36 | 7.36 | 10 | 9.07 | 64% | 67.55% |  |  | 25 | 6
FFL2 | 79130 | 2425855 | 435934 | [6 empty] | 79782 |  |  | 6.62 | 7.1 | 10 | 8.88 | 68% | 67.68% |  |  | 25 | 6
JKL-U2 | 93487 | 2998611 | 564361 | [6 empty] | 102136 |  |  | 8.92 | 8.98 | 10 | 8.43 | 65% | 67.85% |  |  | 25 | 6
GTAL | 8939 | 6632 | 21768 | [6 empty] | 35580 |  |  | 9.11 | 7.44 | 8 | 8.07 | 63% | 6.13% |  |  | 25 | 6
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 133410 | 3797404 | 701577 | [6 empty] | 131604 |  |  | 4.06 | 4.02 | 11 | 9.61 | 78% | 72.7% |  |  | 25 | 6
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-