## Sheet1
Plan vs Achievement
Date: | 20-Sep-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 83873 | 2061190 | 1181830 | [6 empty] | 89825 |  |  | 6.87 | 8.11 | 10 | 9.94 | 68% | 70.87% |  |  | 25 | 16
JAL3 | 10260 | 252869 | 152345 | [6 empty] | 8741 |  |  | 6.44 | 6.87 | 10 | 9.68 | 66% | 72.33% |  |  | 25 | 16
JFL | 46060 | 1022653 | 687239 | [6 empty] | 40617 |  |  | 6.51 | 6.21 | 8 | 8.32 | 71.8% | 75.36% |  |  | 25 | 16
JKL | 66095 | 1740159 | 1054272 | [6 empty] | 69289 |  |  | 10.12 | 9.69 | 9 | 9.75 | 58.8% | 64.98% |  |  | 25 | 16
MFL | 76711 | 2149237 | 1192095 | [6 empty] | 81111 |  |  | 7.36 | 7.28 | 10 | 9.1 | 64% | 68.19% |  |  | 25 | 16
FFL2 | 110842 | 2425855 | 1421835 | [6 empty] | 120904 |  |  | 6.62 | 7.22 | 10 | 10.91 | 68% | 67.28% |  |  | 25 | 16
JKL-U2 | 96124 | 2998611 | 1551554 | [6 empty] | 107454 |  |  | 8.92 | 8.59 | 10 | 8.51 | 65% | 66.87% |  |  | 25 | 16
GTAL | 21830 | 228632 | 94429 | [6 empty] | 31922 |  |  | 9.11 | 5.4 | 8 | 8.19 | 63% | 5.81% |  |  | 25 | 16
GMT TOTAL: | [12 empty] | 7.89 |  | 9.7 |  | 65.66% |  |  |  | 25
LINGERIE | 154858 | 3797404 | 2302204 | [6 empty] | 163427 |  |  | 4.06 | 4.08 | 11 | 11.41 | 78% | 73.04% |  |  | 25 | 16
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-