## Sheet1
Plan vs Achievement
Date: | 01-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 90756 | 2343382 | 90756 | [6 empty] | 86553 |  |  | 7.11 | 6.67 | 10 | 9.86 | 68% | 72.7% |  |  | 26 | 1
JAL3 | 10390 | 285887 | 10390 | [6 empty] | 9874 |  |  | 5.96 | 5.66 | 10 | 8 | 68% | 77.56% |  |  | 26 | 1
JFL | 45505 | 1652169 | 45505 | [6 empty] | 39125 |  |  | 6.07 | 5.82 | 10.5 | 8.13 | 72% | 76.07% |  |  | 26 | 1
JKL | 64757 | 1755763 | 64757 | [6 empty] | 74111 |  |  | 10.32 | 8.79 | 9 | 8.84 | 60% | 61.83% |  |  | 26 | 1
MFL | 87613 | 2319422 | 87613 | [6 empty] | 94092 |  |  | 7.5 | 7.03 | 10 | 10.07 | 64% | 68.89% |  |  | 26 | 1
FFL2 | 93176 | 2196792 | 93176 | [6 empty] | 95149 |  |  | 7.88 | 7.35 | 10 | 12.1 | 68% | 67.73% |  |  | 26 | 1
JKL-U2 | 115477 | 3634362 | 115477 | [6 empty] | 123207 |  |  | 8.67 | 7.52 | 10 | 8.37 | 65% | 69.62% |  |  | 26 | 1
GTAL | 20129 | 335974 | 20129 | [6 empty] | 28522 |  |  | 6.61 | 1.09 | 8 | 8 | 63% | 15.19% |  |  | 26 | 1
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 128960 | 3013766 | 128960 | [6 empty] | 117845 |  |  | 3.89 | 4.16 | 8.82 | 10.92 | 74% | 75.69% |  |  | 26 | 1
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-