## Sheet1
Plan vs Achievement
Date: | 04-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 91485 | 2343382 | 283732 | [6 empty] | 88323 |  |  | 7.11 | 6.75 | 10 | 10.3 | 68% | 72.88% |  |  | 26 | 3
JAL3 | 12150 | 285887 | 34320 | [6 empty] | 11553 |  |  | 5.96 | 5.73 | 10 | 8.54 | 68% | 79.28% |  |  | 26 | 3
JFL | 51225 | 1652169 | 142426 | [6 empty] | 43056 |  |  | 6.07 | 5.63 | 10.5 | 8.26 | 72% | 75.83% |  |  | 26 | 3
JKL | 65854 | 1755763 | 195330 | [6 empty] | 72156 |  |  | 10.32 | 8.84 | 9 | 8.74 | 60% | 62.59% |  |  | 26 | 3
MFL | 88464 | 2319422 | 278081 | [6 empty] | 94399 |  |  | 7.5 | 6.95 | 10 | 10.01 | 64% | 68.33% |  |  | 26 | 3
FFL2 | 91185 | 2196792 | 273942 | [6 empty] | 93994 |  |  | 7.88 | 7.41 | 10 | 12.31 | 68% | 66.02% |  |  | 26 | 3
JKL-U2 | 109213 | 3634362 | 341310 | [6 empty] | 116159 |  |  | 8.67 | 7.53 | 10 | 8.51 | 65% | 69.31% |  |  | 26 | 3
GTAL | 16062 | 335974 | 54366 | [6 empty] | 34296 |  |  | 6.61 | 1.08 | 8 | 8.08 | 63% | 13.4% |  |  | 26 | 3
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 121120 | 3013766 | 369253 | [6 empty] | 119991 |  |  | 3.89 | 4.15 | 8.82 | 10.1 | 74% | 75.81% |  |  | 26 | 3
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-