## Sheet1
Plan vs Achievement
Date: | 18-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 92733 | 2343382 | 1387113 | [6 empty] | 93276 |  |  | 7.11 | 7.01 | 10 | 10.44 | 68% | 72.19% |  |  | 26 | 15
JAL3 | 9600 | 285887 | 173945 | [6 empty] | 9610 |  |  | 5.96 | 6.04 | 10 | 9.23 | 68% | 75.99% |  |  | 26 | 15
JFL | 57173 | 1652169 | 798667 | [6 empty] | 49610 |  |  | 6.07 | 5.39 | 10.5 | 8.93 | 72% | 77.1% |  |  | 26 | 15
JKL | 63617 | 1755763 | 964405 | [6 empty] | 71304 |  |  | 10.32 | 9.77 | 9 | 10.23 | 60% | 59.13% |  |  | 26 | 15
MFL | 80551 | 2319422 | 1214904 | [6 empty] | 85479 |  |  | 7.5 | 7.11 | 10 | 9.41 | 64% | 68.52% |  |  | 26 | 15
FFL2 | 78604 | 2196792 | 1344126 | [6 empty] | 91676 |  |  | 7.88 | 7.67 | 10 | 12.71 | 68% | 62.37% |  |  | 26 | 15
JKL-U2 | 102838 | 3634362 | 1585733 | [6 empty] | 111820 |  |  | 8.67 | 7.88 | 10 | 8.75 | 65% | 67.03% |  |  | 26 | 15
GTAL | 2730 | 335974 | 63827 | [6 empty] | 5480 |  |  | 6.61 | 3.27 | 8 | 8.08 | 63% | 3.6% |  |  | 26 | 15
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 122495 | 3013766 | 1910355 | [6 empty] | 118455 |  |  | 3.89 | 4.13 | 8.82 | 10.23 | 74% | 75.39% |  |  | 26 | 15
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-