## Sheet1
Plan vs Achievement
Date: | 19-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 91015 | 2343382 | 1478128 | [6 empty] | 90492 |  |  | 7.11 | 7.02 | 10 | 10.46 | 68% | 72.12% |  |  | 26 | 16
JAL3 | 8765 | 285887 | 182710 | [6 empty] | 7507 |  |  | 5.96 | 6.08 | 10 | 9.17 | 68% | 75.97% |  |  | 26 | 16
JFL | 60664 | 1652169 | 859331 | [6 empty] | 55032 |  |  | 6.07 | 5.38 | 10.5 | 9.01 | 72% | 76.89% |  |  | 26 | 16
JKL | 62164 | 1755763 | 1027272 | [6 empty] | 69910 |  |  | 10.32 | 9.79 | 9 | 10.22 | 60% | 59.17% |  |  | 26 | 16
MFL | 76611 | 2319422 | 1291515 | [6 empty] | 83452 |  |  | 7.5 | 7.14 | 10 | 9.41 | 64% | 68.52% |  |  | 26 | 16
FFL2 | 77759 | 2196792 | 1421885 | [6 empty] | 89386 |  |  | 7.88 | 7.7 | 10 | 12.67 | 68% | 62.42% |  |  | 26 | 16
JKL-U2 | 101489 | 3634362 | 1687222 | [6 empty] | 113315 |  |  | 8.67 | 7.9 | 10 | 8.75 | 65% | 66.94% |  |  | 26 | 16
GTAL | 2100 | 335974 | 65927 | [6 empty] | 9733 |  |  | 6.61 | 3.27 | 8 | 8.07 | 63% | 3.58% |  |  | 26 | 16
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 116868 | 3013766 | 2027223 | [6 empty] | 110484 |  |  | 3.89 | 4.13 | 8.82 | 10.15 | 74% | 75.58% |  |  | 26 | 16
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-