## Sheet1
Plan vs Achievement
Date: | 22-Oct-25
Production Unit | QC Pass (Pcs) | Plan (Pcs) | Accu. QC Pass | Plan Balance | Required Prod upto yesterday | Back Log upto yesterday | Average Requirement as per Plan | Average target in minutes | QC Pass in minutes | Factory Target | Plan Achv % (monthly, minute based) | Required Hr | Plan SMV | Produced SMV | Plan Hr | Produced Hr | Plan Eff% | Prod. Eff% | Accu. Produced Minute | Total Plan Minute | Plan day | Completed Day | Remaining Days
JAL | 87170 | 2343382 | 1741614 | [6 empty] | 91060 |  |  | 7.11 | 7.03 | 10 | 10.4 | 68% | 72.07% |  |  | 26 | 19
JAL3 | 9850 | 285887 | 213700 | [6 empty] | 9867 |  |  | 5.96 | 6.07 | 10 | 9.07 | 68% | 75.86% |  |  | 26 | 19
JFL | 65258 | 1652169 | 1048152 | [6 empty] | 59917 |  |  | 6.07 | 5.36 | 10.5 | 9.21 | 72% | 77.07% |  |  | 26 | 19
JKL | 56832 | 1755763 | 1201676 | [6 empty] | 65501 |  |  | 10.32 | 9.81 | 9 | 10.11 | 60% | 58.78% |  |  | 26 | 19
MFL | 79309 | 2319422 | 1532842 | [6 empty] | 86999 |  |  | 7.5 | 7.18 | 10 | 9.48 | 64% | 68.13% |  |  | 26 | 19
FFL2 | 83175 | 2196792 | 1661834 | [6 empty] | 96871 |  |  | 7.88 | 7.78 | 10 | 12.6 | 68% | 62.51% |  |  | 26 | 19
JKL-U2 | 101245 | 3634362 | 1994798 | [6 empty] | 115974 |  |  | 8.67 | 7.95 | 10 | 8.74 | 65% | 66.72% |  |  | 26 | 19
GTAL | 10633 | 335974 | 87580 | [6 empty] | 21121 |  |  | 6.61 | 5.38 | 8 | 8.08 | 63% | 4.82% |  |  | 26 | 19
GMT TOTAL: | [12 empty] | 7.89 |  | 9.89 |  | 65.66% |  |  |  | 26
LINGERIE | 120449 | 3013766 | 2377919 | [6 empty] | 111263 |  |  | 3.89 | 4.13 | 8.82 | 9.97 | 74% | 75.88% |  |  | 26 | 19
Forecast excluding Lingerie:
Plan Qty | Production in Completed days | Estimated Production/day | Remaining days Possible Production | Forecasted production | Backlog from plan
-
-
-
-
-